## Overview
BẾP NHỚ – DEVELOPMENT CONTROL CENTER
Metric | Value | Phase | Items | Story Points
Total backlog items | 127 | P0 Foundation | 12 | 69
Must items | 73 | P1 Core Cooking | 22 | 108
In Progress | 0 | P2 Personalization | 11 | 77
Done | 0 | P3 Household & Planning | 11 | 67
|  | P4 Utility | 15 | 71
|  | P5 Discovery & Social | 22 | 100
Recommended first execution slice |  | P6 Business & Growth | 24 | 131
P0 Foundation → P1 vertical slice: Account → Verified Recipe → Cook Mode → Feedback → Taste Signal → Personal Recipe V2. Do not start Social/Payment before this loop is demonstrably reliable and measurable. |  | P7 Production & Native | 10 | 62

## Product Backlog
Backlog ID | Epic | Feature / Req | User Story / Goal | Requirement ID(s) | Priority | Phase | Dependencies | Backend Task | Frontend Task | DB/Data Task | AI/Data Task | QA/Test Task | Acceptance Criteria | Estimate (SP) | Status | Owner | Notes
BN-P0-001 | Engineering Foundation | Repository & Monorepo | Thiết lập monorepo apps/web, apps/api, apps/admin, packages/*, lint/format/commit conventions. | ARCH | Must | P0 Foundation |  | Initialize workspace, dependency boundaries, scripts | N/A | Repo layout + config | N/A | CI validates lint/typecheck | Repo clone → install → lint/typecheck succeeds | 5 | Not Started | Unassigned
BN-P0-002 | Engineering Foundation | Local Dev Stack | Docker Compose cho PostgreSQL, Redis, object storage emulator và mail/test dependencies. | ARCH | Must | P0 Foundation | BN-P0-001 | Compose services + health checks | N/A | Init local databases | N/A | Smoke test service readiness | docker compose up produces healthy stack | 5 | Not Started | Unassigned
BN-P0-003 | Engineering Foundation | CI/CD Baseline | CI lint, typecheck, unit test, build, security scan; environments dev/staging/prod. | NFR-SEC-002,NFR-MNT-001 | Must | P0 Foundation | BN-P0-001 | CI workflows + artifact build | N/A | Migration gate | N/A | Pipeline tests | PR cannot merge when gates fail | 8 | Not Started | Unassigned
BN-P0-004 | Engineering Foundation | API Contract Baseline | OpenAPI conventions, versioning, error envelope, pagination, idempotency. | NFR-MNT-001,NFR-REL-001 | Must | P0 Foundation | BN-P0-001 | API framework/middleware | Generate typed client later | N/A | N/A | Contract tests | OpenAPI validates and error format consistent | 5 | Not Started | Unassigned
BN-P0-005 | Engineering Foundation | Observability Baseline | Structured logs, trace/correlation IDs, metrics, health/readiness endpoints. | NFR-OBS-001 | Must | P0 Foundation | BN-P0-001 | Logging/tracing/metrics middleware | N/A | N/A | N/A | Observability smoke test | Request trace visible end-to-end | 5 | Not Started | Unassigned
BN-P0-006 | Engineering Foundation | Security Baseline | Secrets, RBAC foundation, rate limiting, secure headers, upload limits, dependency scanning. | NFR-SEC-001,NFR-SEC-003 | Must | P0 Foundation | BN-P0-001 | Security middleware + auth hooks | Secure client token storage | N/A | N/A | Security unit/DAST baseline | Baseline controls enabled by default | 8 | Not Started | Unassigned
BN-P0-007 | Engineering Foundation | Database Migration Framework | Migration/seed strategy, canonical IDs, audit timestamps, optimistic locking conventions. | NFR-MNT-001,NFR-DATA-001 | Must | P0 Foundation | BN-P0-002 | ORM/migration tooling | N/A | Migration framework + seed | N/A | Migration forward/backward test | Fresh DB can reach current schema deterministically | 5 | Not Started | Unassigned
BN-P0-008 | Engineering Foundation | Feature Flags & Remote Config | Flag SDK/server evaluation/kill-switch conventions. | FR-ADM-004,BR-019 | Must | P0 Foundation | BN-P0-001 | Feature flag service abstraction | Client flag hooks | flag config tables optional | N/A | Flag behavior tests | Risky features can be disabled without redeploy | 5 | Not Started | Unassigned
BN-P0-009 | Engineering Foundation | Media Foundation | Object storage, direct upload, media metadata, image variants/CDN abstraction. | NFR-COST-001 | Should | P0 Foundation | BN-P0-002 | Signed upload + media service | Uploader component | media_asset schema | N/A | Upload/security tests | Image upload/download works with ownership checks | 5 | Not Started | Unassigned
BN-P0-010 | Engineering Foundation | Test Harness | Unit/integration/e2e fixtures, synthetic recipes/users, test DB reset. | NFR-QUAL-001 | Must | P0 Foundation | BN-P0-002,BN-P0-007 | Test utilities | E2E harness | Seed fixtures | Golden sets later | CI test smoke | Deterministic local/CI test runs | 5 | Not Started | Unassigned
BN-P0-011 | Engineering Foundation | AI Gateway Skeleton | Provider adapter interface, prompt registry, schema validation, timeout/circuit-breaker/cost logging. | AI-004,AI-005,AI-006,NFR-AI-001 | Must | P0 Foundation | BN-P0-004,BN-P0-005 | AI gateway skeleton | N/A | prompt/model config schema | Provider-independent adapter | Fallback/timeout tests | App core runs if AI provider unavailable | 8 | Not Started | Unassigned
BN-P0-012 | Engineering Foundation | Analytics Event Schema | Versioned event naming, identity policy, PII redaction, local event collector. | FR-AN-001,NFR-DATA-001,NFR-PRV-002 | Must | P0 Foundation | BN-P0-005 | Event SDK/server collector | Client event wrapper | event schema registry | N/A | Schema validation tests | Invalid/unversioned events rejected in non-prod | 5 | Not Started | Unassigned
BN-P1-001 | Account & Onboarding | FR-ACC-001 | Với vai trò user, tôi cần đăng ký/đăng nhập bằng email, số điện thoại và social login; hỗ trợ guest mode giới hạn. | FR-ACC-001 | Must | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Auth/profile APIs, validation, session/device logic | Onboarding/profile/auth/device-management UI | identity/profile/session schema + indexes |  | Test functional path + negative/authorization cases for FR-ACC-001 | Không tạo duplicate identity; có cơ chế link account. | 5 | Not Started | Unassigned
BN-P1-002 | Account & Onboarding | FR-ACC-002 | Với vai trò user, tôi cần onboarding thu thập mục tiêu nấu ăn, số người, vùng miền, mức kỹ năng, dụng cụ bếp, thời gian và budget. | FR-ACC-002 | Must | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Auth/profile APIs, validation, session/device logic | Onboarding/profile/auth/device-management UI | identity/profile/session schema + indexes |  | Test functional path + negative/authorization cases for FR-ACC-002 | Có thể skip từng phần; chỉnh lại sau. | 5 | Not Started | Unassigned
BN-P1-003 | Account & Onboarding | FR-ACC-003 | Với vai trò user, tôi cần hồ sơ lưu ngôn ngữ, đơn vị đo, chế độ ăn, dị ứng, nguyên liệu tránh, lịch sử và privacy settings. | FR-ACC-003 | Must | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Auth/profile APIs, validation, session/device logic | Onboarding/profile/auth/device-management UI | identity/profile/session schema + indexes |  | Test functional path + negative/authorization cases for FR-ACC-003 | Dị ứng được ưu tiên hơn mọi recommendation. | 5 | Not Started | Unassigned
BN-P1-004 | Account & Onboarding | FR-ACC-004 | Với vai trò user, tôi cần cho phép export dữ liệu, xóa tài khoản, vô hiệu hóa tài khoản và tải bản sao dữ liệu. | FR-ACC-004 | Must | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Auth/profile APIs, validation, session/device logic | Onboarding/profile/auth/device-management UI | identity/profile/session schema + indexes |  | Test functional path + negative/authorization cases for FR-ACC-004 | Tuân thủ chính sách retention/erasure. | 5 | Not Started | Unassigned
BN-P1-005 | Account & Onboarding | FR-ACC-005 | Với vai trò user, tôi cần hỗ trợ nhiều thiết bị, đồng bộ session và revoke thiết bị. | FR-ACC-005 | Should | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Auth/profile APIs, validation, session/device logic | Onboarding/profile/auth/device-management UI | identity/profile/session schema + indexes |  | Test functional path + negative/authorization cases for FR-ACC-005 | Hiển thị lịch sử đăng nhập bất thường. | 5 | Not Started | Unassigned
BN-P2-006 | Taste DNA & Preference Memory | FR-TASTE-001 | Với vai trò user, tôi cần duy trì Taste DNA theo nhiều chiều: mặn, ngọt, chua, cay, umami, béo, đắng, độ mềm/giòn, độ khô/nước, hành/tỏi, mùi thảo mộc. | FR-TASTE-001 | Must | P2 Personalization | BN-P0-001,BN-P0-004,BN-P0-007, core cook + feedback | Taste profile service, signal ingestion, recompute hooks | Taste DNA visualization/edit/reset UI | taste_profile/taste_signal/taste_dimension schema | Signal weighting, confidence update, context overrides | Test functional path + negative/authorization cases for FR-TASTE-001 | Mỗi dimension có score + confidence + sample count. | 8 | Not Started | Unassigned
BN-P2-007 | Taste DNA & Preference Memory | FR-TASTE-002 | Với vai trò user, tôi cần taste DNA phải học từ onboarding, rating, post-cook feedback, thao tác chỉnh recipe và hành vi lựa chọn. | FR-TASTE-002 | Must | P2 Personalization | BN-P0-001,BN-P0-004,BN-P0-007, core cook + feedback | Taste profile service, signal ingestion, recompute hooks | Taste DNA visualization/edit/reset UI | taste_profile/taste_signal/taste_dimension schema | Signal weighting, confidence update, context overrides | Test functional path + negative/authorization cases for FR-TASTE-002 | Nguồn tín hiệu có trọng số khác nhau. | 8 | Not Started | Unassigned
BN-P2-008 | Taste DNA & Preference Memory | FR-TASTE-003 | Với vai trò user, tôi cần cho phép preference toàn cục, theo nhóm món, theo nguyên liệu và theo recipe cụ thể. | FR-TASTE-003 | Must | P2 Personalization | BN-P0-001,BN-P0-004,BN-P0-007, core cook + feedback | Taste profile service, signal ingestion, recompute hooks | Taste DNA visualization/edit/reset UI | taste_profile/taste_signal/taste_dimension schema | Signal weighting, confidence update, context overrides | Test functional path + negative/authorization cases for FR-TASTE-003 | Context-specific preference override global. | 8 | Not Started | Unassigned
BN-P2-009 | Taste DNA & Preference Memory | FR-TASTE-004 | Với vai trò user, tôi cần hiển thị Taste DNA theo cách dễ hiểu và cho phép user chỉnh thủ công. | FR-TASTE-004 | Should | P2 Personalization | BN-P0-001,BN-P0-004,BN-P0-007, core cook + feedback | Taste profile service, signal ingestion, recompute hooks | Taste DNA visualization/edit/reset UI | taste_profile/taste_signal/taste_dimension schema | Signal weighting, confidence update, context overrides | Test functional path + negative/authorization cases for FR-TASTE-004 | Manual edit được audit và giảm confidence tạm thời. | 5 | Not Started | Unassigned
BN-P2-010 | Taste DNA & Preference Memory | FR-TASTE-005 | Với vai trò user, tôi cần cho phép reset một dimension hoặc toàn bộ Taste DNA mà không xóa lịch sử cook. | FR-TASTE-005 | Could | P2 Personalization | BN-P0-001,BN-P0-004,BN-P0-007, core cook + feedback | Taste profile service, signal ingestion, recompute hooks | Taste DNA visualization/edit/reset UI | taste_profile/taste_signal/taste_dimension schema | Signal weighting, confidence update, context overrides | Test functional path + negative/authorization cases for FR-TASTE-005 | Có cảnh báo hậu quả personalization. | 3 | Not Started | Unassigned
BN-P3-011 | Household & Family Taste | FR-HH-001 | Với vai trò household owner/member, tôi cần tạo household, mời thành viên, guest profile và child profile. | FR-HH-001 | Must | P3 Household & Planning | BN-P0-001,BN-P0-004,BN-P0-007, account + taste | Household RBAC, invite/member/shared-resource services | Household setup/member/taste-conflict UI | household/member/consent/shared-resource schema |  | Test functional path + negative/authorization cases for FR-HH-001 | Role Owner/Admin/Member/Guest. | 5 | Not Started | Unassigned
BN-P3-012 | Household & Family Taste | FR-HH-002 | Với vai trò household owner/member, tôi cần mỗi thành viên có Taste DNA, allergy/diet và serving size riêng. | FR-HH-002 | Must | P3 Household & Planning | BN-P0-001,BN-P0-004,BN-P0-007, account + taste | Household RBAC, invite/member/shared-resource services | Household setup/member/taste-conflict UI | household/member/consent/shared-resource schema |  | Test functional path + negative/authorization cases for FR-HH-002 | Không gộp dữ liệu cá nhân ngoài consent. | 5 | Not Started | Unassigned
BN-P3-013 | Household & Family Taste | FR-HH-003 | Với vai trò household owner/member, tôi cần family Taste Engine đề xuất công thức dung hòa và hướng dẫn tách phần khi preference xung đột. | FR-HH-003 | Must | P3 Household & Planning | BN-P0-001,BN-P0-004,BN-P0-007, account + taste | Household RBAC, invite/member/shared-resource services | Household setup/member/taste-conflict UI | household/member/consent/shared-resource schema |  | Test functional path + negative/authorization cases for FR-HH-003 | Allergy luôn là hard constraint. | 5 | Not Started | Unassigned
BN-P3-014 | Household & Family Taste | FR-HH-004 | Với vai trò household owner/member, tôi cần meal plan, pantry, shopping list có thể dùng chung household và đồng bộ real time. | FR-HH-004 | Must | P3 Household & Planning | BN-P0-001,BN-P0-004,BN-P0-007, account + taste | Household RBAC, invite/member/shared-resource services | Household setup/member/taste-conflict UI | household/member/consent/shared-resource schema |  | Test functional path + negative/authorization cases for FR-HH-004 | Conflict merge có versioning. | 5 | Not Started | Unassigned
BN-P3-015 | Household & Family Taste | FR-HH-005 | Với vai trò household owner/member, tôi cần cho phép lưu “ai ăn bữa này” để recommendation theo đúng nhóm người. | FR-HH-005 | Should | P3 Household & Planning | BN-P0-001,BN-P0-004,BN-P0-007, account + taste | Household RBAC, invite/member/shared-resource services | Household setup/member/taste-conflict UI | household/member/consent/shared-resource schema |  | Test functional path + negative/authorization cases for FR-HH-005 | Có preset: cả nhà, hai người, trẻ em... | 5 | Not Started | Unassigned
BN-P1-016 | Recipe Catalog & Verified Content | FR-REC-001 | Với vai trò user/content editor, tôi cần recipe lưu cấu trúc định lượng: ingredient canonical, quantity, unit, preparation, substitution, step, heat, duration, serving. | FR-REC-001 | Must | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Recipe/CMS domain services, validation, version publishing | Recipe detail/catalog/editor/verified badges UI | recipe/ingredient/version/taxonomy/media schema |  | Test functional path + negative/authorization cases for FR-REC-001 | Không dùng “vừa đủ” làm dữ liệu duy nhất cho gia vị chính. | 5 | Not Started | Unassigned
BN-P1-017 | Recipe Catalog & Verified Content | FR-REC-002 | Với vai trò user/content editor, tôi cần phân loại món theo vùng miền, bữa ăn, kỹ thuật, nguyên liệu, mùa, độ khó, thời gian và chi phí. | FR-REC-002 | Must | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Recipe/CMS domain services, validation, version publishing | Recipe detail/catalog/editor/verified badges UI | recipe/ingredient/version/taxonomy/media schema |  | Test functional path + negative/authorization cases for FR-REC-002 | Taxonomy quản trị qua CMS. | 5 | Not Started | Unassigned
BN-P1-018 | Recipe Catalog & Verified Content | FR-REC-003 | Với vai trò user/content editor, tôi cần mỗi recipe có source/provenance, reviewer, trạng thái draft/verified/published/deprecated. | FR-REC-003 | Must | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Recipe/CMS domain services, validation, version publishing | Recipe detail/catalog/editor/verified badges UI | recipe/ingredient/version/taxonomy/media schema |  | Test functional path + negative/authorization cases for FR-REC-003 | Verified recipe có lịch sử review. | 5 | Not Started | Unassigned
BN-P1-019 | Recipe Catalog & Verified Content | FR-REC-004 | Với vai trò user/content editor, tôi cần hỗ trợ ảnh, video ngắn, step image, nutrition optional và equipment. | FR-REC-004 | Should | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Recipe/CMS domain services, validation, version publishing | Recipe detail/catalog/editor/verified badges UI | recipe/ingredient/version/taxonomy/media schema |  | Test functional path + negative/authorization cases for FR-REC-004 | Media có moderation/licensing metadata. | 5 | Not Started | Unassigned
BN-P1-020 | Recipe Catalog & Verified Content | FR-REC-005 | Với vai trò user/content editor, tôi cần hỗ trợ biến thể Bắc/Trung/Nam/gia đình nhưng vẫn giữ lineage của món gốc. | FR-REC-005 | Should | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Recipe/CMS domain services, validation, version publishing | Recipe detail/catalog/editor/verified badges UI | recipe/ingredient/version/taxonomy/media schema |  | Test functional path + negative/authorization cases for FR-REC-005 | Không overwrite recipe verified gốc. | 5 | Not Started | Unassigned
BN-P1-021 | Recipe Catalog & Verified Content | FR-REC-006 | Với vai trò user/content editor, tôi cần creator/user có thể submit recipe để review hoặc public theo policy. | FR-REC-006 | Should | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Recipe/CMS domain services, validation, version publishing | Recipe detail/catalog/editor/verified badges UI | recipe/ingredient/version/taxonomy/media schema |  | Test functional path + negative/authorization cases for FR-REC-006 | Nội dung community gắn nhãn nguồn rõ ràng. | 5 | Not Started | Unassigned
BN-P2-022 | Recipe Personalization & Evolution | FR-EVO-001 | Với vai trò user, tôi cần sinh bản recipe cá nhân dựa trên Taste DNA, serving, household, diet, equipment và history. | FR-EVO-001 | Must | P2 Personalization | BN-P0-001,BN-P0-004,BN-P0-007, core cook + feedback | Personalization/version/diff/rollback/fork services | Personalized diff/version compare/pin/rollback/fork UI | personal_recipe_version/diff/lineage/adjustment schema | Adjustment rules + explanation generation + guardrails | Test functional path + negative/authorization cases for FR-EVO-001 | Luôn hiển thị các thay đổi so với bản chuẩn. | 8 | Not Started | Unassigned
BN-P2-023 | Recipe Personalization & Evolution | FR-EVO-002 | Với vai trò user, tôi cần sau cook feedback, tạo version V2/V3... với diff định lượng, lý do và confidence. | FR-EVO-002 | Must | P2 Personalization | BN-P0-001,BN-P0-004,BN-P0-007, core cook + feedback | Personalization/version/diff/rollback/fork services | Personalized diff/version compare/pin/rollback/fork UI | personal_recipe_version/diff/lineage/adjustment schema | Adjustment rules + explanation generation + guardrails | Test functional path + negative/authorization cases for FR-EVO-002 | Không thay đổi silent; user có thể accept/reject. | 8 | Not Started | Unassigned
BN-P2-024 | Recipe Personalization & Evolution | FR-EVO-003 | Với vai trò user, tôi cần user có thể pin một version làm “My Best Version”, rollback hoặc compare 2 versions. | FR-EVO-003 | Must | P2 Personalization | BN-P0-001,BN-P0-004,BN-P0-007, core cook + feedback | Personalization/version/diff/rollback/fork services | Personalized diff/version compare/pin/rollback/fork UI | personal_recipe_version/diff/lineage/adjustment schema | Adjustment rules + explanation generation + guardrails | Test functional path + negative/authorization cases for FR-EVO-003 | Lineage không bị mất. | 8 | Not Started | Unassigned
BN-P2-025 | Recipe Personalization & Evolution | FR-EVO-004 | Với vai trò user, tôi cần recipe Fork: fork recipe của creator/user khác thành nhánh riêng và giữ attribution. | FR-EVO-004 | Should | P2 Personalization | BN-P0-001,BN-P0-004,BN-P0-007, core cook + feedback | Personalization/version/diff/rollback/fork services | Personalized diff/version compare/pin/rollback/fork UI | personal_recipe_version/diff/lineage/adjustment schema | Adjustment rules + explanation generation + guardrails | Test functional path + negative/authorization cases for FR-EVO-004 | Có source chain và license rules. | 5 | Not Started | Unassigned
BN-P2-026 | Recipe Personalization & Evolution | FR-EVO-005 | Với vai trò user, tôi cần tự động scale recipe theo serving nhưng giữ ratio/constraint đặc thù. | FR-EVO-005 | Must | P2 Personalization | BN-P0-001,BN-P0-004,BN-P0-007, core cook + feedback | Personalization/version/diff/rollback/fork services | Personalized diff/version compare/pin/rollback/fork UI | personal_recipe_version/diff/lineage/adjustment schema | Adjustment rules + explanation generation + guardrails | Test functional path + negative/authorization cases for FR-EVO-005 | Có rounding rule theo unit/ingredient. | 8 | Not Started | Unassigned
BN-P2-027 | Recipe Personalization & Evolution | FR-EVO-006 | Với vai trò user, tôi cần không tự thay đổi ingredient liên quan dị ứng/an toàn nếu không có xác nhận. | FR-EVO-006 | Must | P2 Personalization | BN-P0-001,BN-P0-004,BN-P0-007, core cook + feedback | Personalization/version/diff/rollback/fork services | Personalized diff/version compare/pin/rollback/fork UI | personal_recipe_version/diff/lineage/adjustment schema | Adjustment rules + explanation generation + guardrails | Test functional path + negative/authorization cases for FR-EVO-006 | Safety constraint hard-coded. | 8 | Not Started | Unassigned
BN-P1-028 | Cook Mode & Hands-free | FR-COOK-001 | Với vai trò cook, tôi cần cook Mode hiển thị từng bước lớn, ingredient tại bước, timer, nhiệt độ và progress. | FR-COOK-001 | Must | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Cook session state machine, timers/events/offline sync APIs | Step-by-step Cook Mode/timer/voice/offline UX | cook_session/cook_event/timer/deviation schema |  | Test functional path + negative/authorization cases for FR-COOK-001 | Screen-awake optional; font lớn. | 5 | Not Started | Unassigned
BN-P1-029 | Cook Mode & Hands-free | FR-COOK-002 | Với vai trò cook, tôi cần voice/hands-free command: tiếp theo, quay lại, đặt timer, đọc lại, còn bao lâu, đổi khẩu phần. | FR-COOK-002 | Should | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Cook session state machine, timers/events/offline sync APIs | Step-by-step Cook Mode/timer/voice/offline UX | cook_session/cook_event/timer/deviation schema |  | Test functional path + negative/authorization cases for FR-COOK-002 | Không yêu cầu chạm màn hình trong luồng chính. | 5 | Not Started | Unassigned
BN-P1-030 | Cook Mode & Hands-free | FR-COOK-003 | Với vai trò cook, tôi cần hỗ trợ nhiều timer đồng thời, background notification và resume session. | FR-COOK-003 | Must | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Cook session state machine, timers/events/offline sync APIs | Step-by-step Cook Mode/timer/voice/offline UX | cook_session/cook_event/timer/deviation schema |  | Test functional path + negative/authorization cases for FR-COOK-003 | Không mất timer khi app background/crash. | 5 | Not Started | Unassigned
BN-P1-031 | Cook Mode & Hands-free | FR-COOK-004 | Với vai trò cook, tôi cần cho phép log thay thế nguyên liệu, quantity thực tế, thời gian thực tế và deviation ngay khi nấu. | FR-COOK-004 | Should | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Cook session state machine, timers/events/offline sync APIs | Step-by-step Cook Mode/timer/voice/offline UX | cook_session/cook_event/timer/deviation schema |  | Test functional path + negative/authorization cases for FR-COOK-004 | Dữ liệu dùng cho diagnosis/learning. | 5 | Not Started | Unassigned
BN-P1-032 | Cook Mode & Hands-free | FR-COOK-005 | Với vai trò cook, tôi cần offline cooking cache cho recipe đã mở/lưu. | FR-COOK-005 | Should | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Cook session state machine, timers/events/offline sync APIs | Step-by-step Cook Mode/timer/voice/offline UX | cook_session/cook_event/timer/deviation schema |  | Test functional path + negative/authorization cases for FR-COOK-005 | Feedback sync lại khi có mạng. | 5 | Not Started | Unassigned
BN-P1-033 | Cook Mode & Hands-free | FR-COOK-006 | Với vai trò cook, tôi cần camera optional để ghi ảnh trước/sau và gắn vào cook history. | FR-COOK-006 | Could | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Cook session state machine, timers/events/offline sync APIs | Step-by-step Cook Mode/timer/voice/offline UX | cook_session/cook_event/timer/deviation schema |  | Test functional path + negative/authorization cases for FR-COOK-006 | Media privacy mặc định private. | 3 | Not Started | Unassigned
BN-P1-034 | Feedback & Cooking Memory | FR-FB-001 | Với vai trò cook, tôi cần feedback nhanh sau bữa: mặn/ngọt/chua/cay/béo/texture/nước + overall score. | FR-FB-001 | Must | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Feedback ingestion, revision, cooking-memory aggregation | 10-second feedback, notes, cooking history/timeline UI | feedback/cooking_memory/revision schema |  | Test functional path + negative/authorization cases for FR-FB-001 | Hoàn thành <= 10 giây. | 5 | Not Started | Unassigned
BN-P1-035 | Feedback & Cooking Memory | FR-FB-002 | Với vai trò cook, tôi cần cho phép free-text note, voice note và ghi chú riêng tư. | FR-FB-002 | Should | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Feedback ingestion, revision, cooking-memory aggregation | 10-second feedback, notes, cooking history/timeline UI | feedback/cooking_memory/revision schema |  | Test functional path + negative/authorization cases for FR-FB-002 | Private by default. | 5 | Not Started | Unassigned
BN-P1-036 | Feedback & Cooking Memory | FR-FB-003 | Với vai trò cook, tôi cần cooking Memory lưu thời gian, household members, actual ingredients, feedback và ảnh. | FR-FB-003 | Must | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Feedback ingestion, revision, cooking-memory aggregation | 10-second feedback, notes, cooking history/timeline UI | feedback/cooking_memory/revision schema |  | Test functional path + negative/authorization cases for FR-FB-003 | Có timeline theo món/ngày. | 5 | Not Started | Unassigned
BN-P1-037 | Feedback & Cooking Memory | FR-FB-004 | Với vai trò cook, tôi cần app phát hiện feedback mâu thuẫn/thiếu dữ liệu và hỏi follow-up tối thiểu. | FR-FB-004 | Should | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Feedback ingestion, revision, cooking-memory aggregation | 10-second feedback, notes, cooking history/timeline UI | feedback/cooking_memory/revision schema |  | Test functional path + negative/authorization cases for FR-FB-004 | Không gây fatigue. | 5 | Not Started | Unassigned
BN-P1-038 | Feedback & Cooking Memory | FR-FB-005 | Với vai trò cook, tôi cần user có thể sửa feedback cũ; engine re-compute ảnh hưởng khi cần. | FR-FB-005 | Should | P1 Core Cooking | BN-P0-001,BN-P0-004,BN-P0-007 | Feedback ingestion, revision, cooking-memory aggregation | 10-second feedback, notes, cooking history/timeline UI | feedback/cooking_memory/revision schema |  | Test functional path + negative/authorization cases for FR-FB-005 | Audit revision retained. | 5 | Not Started | Unassigned
BN-P3-039 | Meal Planning | FR-MEAL-001 | Với vai trò user/household, tôi cần sinh meal plan ngày/tuần/tháng theo household, budget, time, pantry, preference và lịch sử. | FR-MEAL-001 | Must | P3 Household & Planning | BN-P0-001,BN-P0-004,BN-P0-007, recipe + household | Planner constraint engine, plan CRUD/regeneration | Calendar/plan generator/lock/regenerate/drag-drop UI | meal_plan/meal_item/template/constraint schema | Constraint optimization/scoring + explanation | Test functional path + negative/authorization cases for FR-MEAL-001 | Có regenerate từng bữa hoặc toàn plan. | 8 | Not Started | Unassigned
BN-P3-040 | Meal Planning | FR-MEAL-002 | Với vai trò user/household, tôi cần hiểu cấu trúc mâm cơm Việt: cơm + món mặn + rau + canh + món phụ/nước chấm. | FR-MEAL-002 | Must | P3 Household & Planning | BN-P0-001,BN-P0-004,BN-P0-007, recipe + household | Planner constraint engine, plan CRUD/regeneration | Calendar/plan generator/lock/regenerate/drag-drop UI | meal_plan/meal_item/template/constraint schema | Constraint optimization/scoring + explanation | Test functional path + negative/authorization cases for FR-MEAL-002 | Tránh xung đột hương vị/kỹ thuật quá giống. | 8 | Not Started | Unassigned
BN-P3-041 | Meal Planning | FR-MEAL-003 | Với vai trò user/household, tôi cần cho phép khóa món/bữa/ngày và regenerate phần còn lại. | FR-MEAL-003 | Must | P3 Household & Planning | BN-P0-001,BN-P0-004,BN-P0-007, recipe + household | Planner constraint engine, plan CRUD/regeneration | Calendar/plan generator/lock/regenerate/drag-drop UI | meal_plan/meal_item/template/constraint schema | Constraint optimization/scoring + explanation | Test functional path + negative/authorization cases for FR-MEAL-003 | Khóa không bị engine overwrite. | 8 | Not Started | Unassigned
BN-P3-042 | Meal Planning | FR-MEAL-004 | Với vai trò user/household, tôi cần tối ưu tái sử dụng nguyên liệu giữa các ngày để giảm lãng phí và số lần đi chợ. | FR-MEAL-004 | Must | P3 Household & Planning | BN-P0-001,BN-P0-004,BN-P0-007, recipe + household | Planner constraint engine, plan CRUD/regeneration | Calendar/plan generator/lock/regenerate/drag-drop UI | meal_plan/meal_item/template/constraint schema | Constraint optimization/scoring + explanation | Test functional path + negative/authorization cases for FR-MEAL-004 | Có explanation về reuse. | 8 | Not Started | Unassigned
BN-P3-043 | Meal Planning | FR-MEAL-005 | Với vai trò user/household, tôi cần calendar view, drag-drop, meal template, recurring plan, ăn ngoài/skipped meal. | FR-MEAL-005 | Should | P3 Household & Planning | BN-P0-001,BN-P0-004,BN-P0-007, recipe + household | Planner constraint engine, plan CRUD/regeneration | Calendar/plan generator/lock/regenerate/drag-drop UI | meal_plan/meal_item/template/constraint schema | Constraint optimization/scoring + explanation | Test functional path + negative/authorization cases for FR-MEAL-005 | Không tính shopping cho bữa ăn ngoài. | 5 | Not Started | Unassigned
BN-P3-044 | Meal Planning | FR-MEAL-006 | Với vai trò user/household, tôi cần theo dõi estimate cost, prep time, cooking load và diversity. | FR-MEAL-006 | Should | P3 Household & Planning | BN-P0-001,BN-P0-004,BN-P0-007, recipe + household | Planner constraint engine, plan CRUD/regeneration | Calendar/plan generator/lock/regenerate/drag-drop UI | meal_plan/meal_item/template/constraint schema | Constraint optimization/scoring + explanation | Test functional path + negative/authorization cases for FR-MEAL-006 | Cost source có timestamp/region. | 5 | Not Started | Unassigned
BN-P4-045 | Pantry & Leftovers | FR-PAN-001 | Với vai trò user/household, tôi cần pantry lưu ingredient, quantity, unit, purchase/open/expiry date, location và household owner. | FR-PAN-001 | Must | P4 Utility | BN-P0-001,BN-P0-004,BN-P0-007, recipe + meal | Inventory ledger, expiry, deduction/undo/reconciliation | Pantry/expiry/leftover/stock adjustment UI | pantry_batch/leftover/inventory_ledger schema |  | Test functional path + negative/authorization cases for FR-PAN-001 | Hỗ trợ manual + barcode/receipt/image optional. | 5 | Not Started | Unassigned
BN-P4-046 | Pantry & Leftovers | FR-PAN-002 | Với vai trò user/household, tôi cần trừ tồn kho từ cook session và cho phép confirm/edit trước khi commit. | FR-PAN-002 | Must | P4 Utility | BN-P0-001,BN-P0-004,BN-P0-007, recipe + meal | Inventory ledger, expiry, deduction/undo/reconciliation | Pantry/expiry/leftover/stock adjustment UI | pantry_batch/leftover/inventory_ledger schema |  | Test functional path + negative/authorization cases for FR-PAN-002 | Không âm tồn kho silent. | 5 | Not Started | Unassigned
BN-P4-047 | Pantry & Leftovers | FR-PAN-003 | Với vai trò user/household, tôi cần cảnh báo nguyên liệu sắp hết hạn và ưu tiên recommendation sử dụng trước. | FR-PAN-003 | Must | P4 Utility | BN-P0-001,BN-P0-004,BN-P0-007, recipe + meal | Inventory ledger, expiry, deduction/undo/reconciliation | Pantry/expiry/leftover/stock adjustment UI | pantry_batch/leftover/inventory_ledger schema |  | Test functional path + negative/authorization cases for FR-PAN-003 | User cấu hình threshold. | 5 | Not Started | Unassigned
BN-P4-048 | Pantry & Leftovers | FR-PAN-004 | Với vai trò user/household, tôi cần leftover object lưu món còn lại, quantity, ngày nấu, storage và use-by. | FR-PAN-004 | Should | P4 Utility | BN-P0-001,BN-P0-004,BN-P0-007, recipe + meal | Inventory ledger, expiry, deduction/undo/reconciliation | Pantry/expiry/leftover/stock adjustment UI | pantry_batch/leftover/inventory_ledger schema |  | Test functional path + negative/authorization cases for FR-PAN-004 | Gợi ý reheat/transform an toàn. | 5 | Not Started | Unassigned
BN-P4-049 | Pantry & Leftovers | FR-PAN-005 | Với vai trò user/household, tôi cần “Nấu từ những gì đang có” lọc món theo coverage pantry và missing ingredients. | FR-PAN-005 | Must | P4 Utility | BN-P0-001,BN-P0-004,BN-P0-007, recipe + meal | Inventory ledger, expiry, deduction/undo/reconciliation | Pantry/expiry/leftover/stock adjustment UI | pantry_batch/leftover/inventory_ledger schema |  | Test functional path + negative/authorization cases for FR-PAN-005 | Hiển thị % coverage và món cần mua thêm. | 5 | Not Started | Unassigned
BN-P4-050 | Pantry & Leftovers | FR-PAN-006 | Với vai trò user/household, tôi cần hỗ trợ household stock reconciliation và inventory adjustment log. | FR-PAN-006 | Could | P4 Utility | BN-P0-001,BN-P0-004,BN-P0-007, recipe + meal | Inventory ledger, expiry, deduction/undo/reconciliation | Pantry/expiry/leftover/stock adjustment UI | pantry_batch/leftover/inventory_ledger schema |  | Test functional path + negative/authorization cases for FR-PAN-006 | Phục vụ user dùng thường xuyên. | 3 | Not Started | Unassigned
BN-P4-051 | Shopping & Budget | FR-SHOP-001 | Với vai trò user/household, tôi cần sinh shopping list từ meal plan/pantry, merge ingredient theo canonical unit. | FR-SHOP-001 | Must | P4 Utility | BN-P0-001,BN-P0-004,BN-P0-007, recipe + meal | List generation/merge/budget/spend services | Shopping list/budget/check-off/spend UI | shopping_list/item/budget/spend schema |  | Test functional path + negative/authorization cases for FR-SHOP-001 | Trừ tồn kho khả dụng. | 5 | Not Started | Unassigned
BN-P4-052 | Shopping & Budget | FR-SHOP-002 | Với vai trò user/household, tôi cần chia list theo nhóm hàng/chợ/siêu thị và người phụ trách. | FR-SHOP-002 | Should | P4 Utility | BN-P0-001,BN-P0-004,BN-P0-007, recipe + meal | List generation/merge/budget/spend services | Shopping list/budget/check-off/spend UI | shopping_list/item/budget/spend schema |  | Test functional path + negative/authorization cases for FR-SHOP-002 | Real-time shared check-off. | 5 | Not Started | Unassigned
BN-P4-053 | Shopping & Budget | FR-SHOP-003 | Với vai trò user/household, tôi cần cho phép budget mục tiêu theo tuần/tháng và cảnh báo plan vượt budget. | FR-SHOP-003 | Must | P4 Utility | BN-P0-001,BN-P0-004,BN-P0-007, recipe + meal | List generation/merge/budget/spend services | Shopping list/budget/check-off/spend UI | shopping_list/item/budget/spend schema |  | Test functional path + negative/authorization cases for FR-SHOP-003 | Recommendation đề xuất thay món/nguyên liệu. | 5 | Not Started | Unassigned
BN-P4-054 | Shopping & Budget | FR-SHOP-004 | Với vai trò user/household, tôi cần theo dõi actual spend và học mức giá user nhập để ước tính tốt hơn. | FR-SHOP-004 | Should | P4 Utility | BN-P0-001,BN-P0-004,BN-P0-007, recipe + meal | List generation/merge/budget/spend services | Shopping list/budget/check-off/spend UI | shopping_list/item/budget/spend schema |  | Test functional path + negative/authorization cases for FR-SHOP-004 | Không giả định giá realtime khi không có nguồn. | 5 | Not Started | Unassigned
BN-P4-055 | Shopping & Budget | FR-SHOP-005 | Với vai trò user/household, tôi cần affiliate/deep link mua nguyên liệu là optional và phải phân biệt rõ nội dung tài trợ. | FR-SHOP-005 | Could | P4 Utility | BN-P0-001,BN-P0-004,BN-P0-007, recipe + meal | List generation/merge/budget/spend services | Shopping list/budget/check-off/spend UI | shopping_list/item/budget/spend schema |  | Test functional path + negative/authorization cases for FR-SHOP-005 | Không ảnh hưởng ranking nếu không khai báo. | 3 | Not Started | Unassigned
BN-P4-056 | Rescue & Substitution | FR-RES-001 | Với vai trò cook, tôi cần rescue Mode cho các lỗi: mặn, nhạt, ngọt, chua, cay, loãng, đặc, cháy nhẹ, sống/dai, tanh. | FR-RES-001 | Must | P4 Utility | BN-P0-001,BN-P0-004,BN-P0-007, recipe + cook | Rescue decision service + substitution graph | Rescue wizard/substitution result/outcome UI | rescue_session/substitution_rule/outcome schema | Rule-based rescue/substitution + bounded AI explanation | Test functional path + negative/authorization cases for FR-RES-001 | Hỏi context tối thiểu trước khi hướng dẫn. | 5 | Not Started | Unassigned
BN-P4-057 | Rescue & Substitution | FR-RES-002 | Với vai trò cook, tôi cần đưa hướng dẫn cứu món theo lượng thực tế, không chỉ lời khuyên chung. | FR-RES-002 | Must | P4 Utility | BN-P0-001,BN-P0-004,BN-P0-007, recipe + cook | Rescue decision service + substitution graph | Rescue wizard/substitution result/outcome UI | rescue_session/substitution_rule/outcome schema | Rule-based rescue/substitution + bounded AI explanation | Test functional path + negative/authorization cases for FR-RES-002 | Có risk warning khi không thể cứu an toàn. | 5 | Not Started | Unassigned
BN-P4-058 | Rescue & Substitution | FR-RES-003 | Với vai trò cook, tôi cần smart substitution đề xuất thay thế theo chức năng ingredient, taste impact, allergy và pantry. | FR-RES-003 | Must | P4 Utility | BN-P0-001,BN-P0-004,BN-P0-007, recipe + cook | Rescue decision service + substitution graph | Rescue wizard/substitution result/outcome UI | rescue_session/substitution_rule/outcome schema | Rule-based rescue/substitution + bounded AI explanation | Test functional path + negative/authorization cases for FR-RES-003 | Hiển thị mức độ tương đương. | 5 | Not Started | Unassigned
BN-P4-059 | Rescue & Substitution | FR-RES-004 | Với vai trò cook, tôi cần sau rescue, cho phép user báo kết quả để engine cải thiện recommendation. | FR-RES-004 | Should | P4 Utility | BN-P0-001,BN-P0-004,BN-P0-007, recipe + cook | Rescue decision service + substitution graph | Rescue wizard/substitution result/outcome UI | rescue_session/substitution_rule/outcome schema | Rule-based rescue/substitution + bounded AI explanation | Test functional path + negative/authorization cases for FR-RES-004 | Không cập nhật taste preference từ lỗi kỹ thuật một cách trực tiếp. | 5 | Not Started | Unassigned
BN-P5-060 | Search & Recommendation | FR-SRCH-001 | Với vai trò user, tôi cần search theo tên, ingredient, vùng miền, thời gian, budget, equipment, diet, skill, pantry coverage. | FR-SRCH-001 | Must | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007, recipe + taste | Search/recommendation candidate/ranking APIs | Search/facets/home recommendation/explanation UI | search index/recommendation event schema | Candidate/ranking/diversity/TasteFit explanation | Test functional path + negative/authorization cases for FR-SRCH-001 | Faceted filtering + typo tolerant. | 5 | Not Started | Unassigned
BN-P5-061 | Search & Recommendation | FR-SRCH-002 | Với vai trò user, tôi cần home recommendation kết hợp Taste DNA, household, recent meals, season, pantry, trend và exploration. | FR-SRCH-002 | Must | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007, recipe + taste | Search/recommendation candidate/ranking APIs | Search/facets/home recommendation/explanation UI | search index/recommendation event schema | Candidate/ranking/diversity/TasteFit explanation | Test functional path + negative/authorization cases for FR-SRCH-002 | Có explanation “vì sao bạn thấy món này”. | 5 | Not Started | Unassigned
BN-P5-062 | Search & Recommendation | FR-SRCH-003 | Với vai trò user, tôi cần không lặp món quá dày và tránh filter bubble bằng exploration có kiểm soát. | FR-SRCH-003 | Should | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007, recipe + taste | Search/recommendation candidate/ranking APIs | Search/facets/home recommendation/explanation UI | search index/recommendation event schema | Candidate/ranking/diversity/TasteFit explanation | Test functional path + negative/authorization cases for FR-SRCH-003 | Diversity constraints configurable. | 5 | Not Started | Unassigned
BN-P5-063 | Search & Recommendation | FR-SRCH-004 | Với vai trò user, tôi cần recommendation phải xử lý cold-start và anonymous user. | FR-SRCH-004 | Must | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007, recipe + taste | Search/recommendation candidate/ranking APIs | Search/facets/home recommendation/explanation UI | search index/recommendation event schema | Candidate/ranking/diversity/TasteFit explanation | Test functional path + negative/authorization cases for FR-SRCH-004 | Fallback editorial/popular/seasonal. | 5 | Not Started | Unassigned
BN-P5-064 | Search & Recommendation | FR-SRCH-005 | Với vai trò user, tôi cần user có thể dislike/not interested và hide creator/tag. | FR-SRCH-005 | Should | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007, recipe + taste | Search/recommendation candidate/ranking APIs | Search/facets/home recommendation/explanation UI | search index/recommendation event schema | Candidate/ranking/diversity/TasteFit explanation | Test functional path + negative/authorization cases for FR-SRCH-005 | Feedback tác động ranking ngay. | 5 | Not Started | Unassigned
BN-P5-065 | Social & Taste Match | FR-SOC-001 | Với vai trò community user, tôi cần feed cho phép post ảnh/video món, recipe reference, cook result, tip, câu hỏi và story ngắn. | FR-SOC-001 | Should | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007, account + recipe + moderation foundation | Feed/social graph/post/comment/reaction/report APIs | Feed/profile/follow/comment/save/report/taste-match UI | social_graph/post/comment/reaction/report schema | Taste Match scoring + feed relevance/moderation assist | Test functional path + negative/authorization cases for FR-SOC-001 | Privacy public/follower/household/private. | 5 | Not Started | Unassigned
BN-P5-066 | Social & Taste Match | FR-SOC-002 | Với vai trò community user, tôi cần follow user/creator/topic/recipe; like/save/comment/share/report. | FR-SOC-002 | Should | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007, account + recipe + moderation foundation | Feed/social graph/post/comment/reaction/report APIs | Feed/profile/follow/comment/save/report/taste-match UI | social_graph/post/comment/reaction/report schema | Taste Match scoring + feed relevance/moderation assist | Test functional path + negative/authorization cases for FR-SOC-002 | Anti-spam/rate limit. | 5 | Not Started | Unassigned
BN-P5-067 | Social & Taste Match | FR-SOC-003 | Với vai trò community user, tôi cần taste Match tính độ tương đồng khẩu vị và dùng để xếp hạng review/recipe. | FR-SOC-003 | Should | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007, account + recipe + moderation foundation | Feed/social graph/post/comment/reaction/report APIs | Feed/profile/follow/comment/save/report/taste-match UI | social_graph/post/comment/reaction/report schema | Taste Match scoring + feed relevance/moderation assist | Test functional path + negative/authorization cases for FR-SOC-003 | Không công khai vector raw nếu user không opt-in. | 5 | Not Started | Unassigned
BN-P5-068 | Social & Taste Match | FR-SOC-004 | Với vai trò community user, tôi cần hiển thị “người có khẩu vị giống bạn” và recipe được họ đánh giá cao. | FR-SOC-004 | Should | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007, account + recipe + moderation foundation | Feed/social graph/post/comment/reaction/report APIs | Feed/profile/follow/comment/save/report/taste-match UI | social_graph/post/comment/reaction/report schema | Taste Match scoring + feed relevance/moderation assist | Test functional path + negative/authorization cases for FR-SOC-004 | Có block/hide. | 5 | Not Started | Unassigned
BN-P5-069 | Social & Taste Match | FR-SOC-005 | Với vai trò community user, tôi cần recipe Fork/Remix hiển thị cây lineage, attribution và popularity của nhánh. | FR-SOC-005 | Should | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007, account + recipe + moderation foundation | Feed/social graph/post/comment/reaction/report APIs | Feed/profile/follow/comment/save/report/taste-match UI | social_graph/post/comment/reaction/report schema | Taste Match scoring + feed relevance/moderation assist | Test functional path + negative/authorization cases for FR-SOC-005 | Original creator nhận attribution. | 5 | Not Started | Unassigned
BN-P5-070 | Social & Taste Match | FR-SOC-006 | Với vai trò community user, tôi cần challenge theo tuần/tháng: nấu 3 món rau, món vùng miền, zero-waste... | FR-SOC-006 | Could | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007, account + recipe + moderation foundation | Feed/social graph/post/comment/reaction/report APIs | Feed/profile/follow/comment/save/report/taste-match UI | social_graph/post/comment/reaction/report schema | Taste Match scoring + feed relevance/moderation assist | Test functional path + negative/authorization cases for FR-SOC-006 | Không dùng dark pattern gây nghiện. | 3 | Not Started | Unassigned
BN-P5-071 | Social & Taste Match | FR-SOC-007 | Với vai trò community user, tôi cần dM/Group chat không bắt buộc ở release đầu nhưng kiến trúc phải không cản trở mở rộng. | FR-SOC-007 | Could | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007, account + recipe + moderation foundation | Feed/social graph/post/comment/reaction/report APIs | Feed/profile/follow/comment/save/report/taste-match UI | social_graph/post/comment/reaction/report schema | Taste Match scoring + feed relevance/moderation assist | Test functional path + negative/authorization cases for FR-SOC-007 | Nếu triển khai cần abuse controls riêng. | 3 | Not Started | Unassigned
BN-P5-072 | Creator Ecosystem | FR-CRT-001 | Với vai trò creator, tôi cần creator profile có bio, specialty, verified badge, recipe collection, followers và analytics. | FR-CRT-001 | Should | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007, account + recipe + moderation foundation | Creator publishing/profile/analytics APIs | Creator profile/editor/collection/analytics UI | creator_profile/collection/analytics aggregate schema |  | Test functional path + negative/authorization cases for FR-CRT-001 | Verification workflow qua Admin. | 5 | Not Started | Unassigned
BN-P5-073 | Creator Ecosystem | FR-CRT-002 | Với vai trò creator, tôi cần creator Studio hỗ trợ draft, version, schedule publish, media, ingredient structured editor. | FR-CRT-002 | Should | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007, account + recipe + moderation foundation | Creator publishing/profile/analytics APIs | Creator profile/editor/collection/analytics UI | creator_profile/collection/analytics aggregate schema |  | Test functional path + negative/authorization cases for FR-CRT-002 | Recipe validation trước publish. | 5 | Not Started | Unassigned
BN-P5-074 | Creator Ecosystem | FR-CRT-003 | Với vai trò creator, tôi cần creator xem analytics aggregate: views, saves, cooks, success feedback, fork count. | FR-CRT-003 | Should | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007, account + recipe + moderation foundation | Creator publishing/profile/analytics APIs | Creator profile/editor/collection/analytics UI | creator_profile/collection/analytics aggregate schema |  | Test functional path + negative/authorization cases for FR-CRT-003 | Không tiết lộ dữ liệu cá nhân user. | 5 | Not Started | Unassigned
BN-P5-075 | Creator Ecosystem | FR-CRT-004 | Với vai trò creator, tôi cần hỗ trợ revenue share/paid collection trong tương lai qua entitlement. | FR-CRT-004 | Could | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007, account + recipe + moderation foundation | Creator publishing/profile/analytics APIs | Creator profile/editor/collection/analytics UI | creator_profile/collection/analytics aggregate schema |  | Test functional path + negative/authorization cases for FR-CRT-004 | Tách khỏi core subscription ledger. | 3 | Not Started | Unassigned
BN-P5-076 | Gamification & Retention | FR-GAME-001 | Với vai trò user, tôi cần streak, cooking milestone, badge và collection phải phản ánh giá trị thực, không ép engagement. | FR-GAME-001 | Could | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007, account + recipe + moderation foundation | Challenge/progress/achievement service | Challenge/progress/badge UI | challenge/achievement/progress/reward schema |  | Test functional path + negative/authorization cases for FR-GAME-001 | Cho phép tắt gamification. | 3 | Not Started | Unassigned
BN-P5-077 | Gamification & Retention | FR-GAME-002 | Với vai trò user, tôi cần weekly recap: món đã nấu, tiết kiệm, ingredient dùng hết, taste learning mới. | FR-GAME-002 | Should | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007, account + recipe + moderation foundation | Challenge/progress/achievement service | Challenge/progress/badge UI | challenge/achievement/progress/reward schema |  | Test functional path + negative/authorization cases for FR-GAME-002 | Có opt-out. | 5 | Not Started | Unassigned
BN-P5-078 | Gamification & Retention | FR-GAME-003 | Với vai trò user, tôi cần seasonal missions/challenges được CMS cấu hình. | FR-GAME-003 | Could | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007, account + recipe + moderation foundation | Challenge/progress/achievement service | Challenge/progress/badge UI | challenge/achievement/progress/reward schema |  | Test functional path + negative/authorization cases for FR-GAME-003 | Moderation cho user-generated challenge nếu có. | 3 | Not Started | Unassigned
BN-P5-079 | Notifications | FR-NOTI-001 | Với vai trò user, tôi cần push/in-app/email cho meal reminder, pantry expiry, shared list change, comment/follow, billing và system notice. | FR-NOTI-001 | Must | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007 | Preference scheduler + push/email/in-app delivery pipeline | Notification center/preferences/deep-link UI | notification/preference/delivery log schema |  | Test functional path + negative/authorization cases for FR-NOTI-001 | User chọn channel/topic/quiet hours. | 5 | Not Started | Unassigned
BN-P5-080 | Notifications | FR-NOTI-002 | Với vai trò user, tôi cần notification phải deep-link đúng context và deduplicate. | FR-NOTI-002 | Must | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007 | Preference scheduler + push/email/in-app delivery pipeline | Notification center/preferences/deep-link UI | notification/preference/delivery log schema |  | Test functional path + negative/authorization cases for FR-NOTI-002 | Có inbox trạng thái read/unread. | 5 | Not Started | Unassigned
BN-P5-081 | Notifications | FR-NOTI-003 | Với vai trò user, tôi cần digest thay cho spam khi nhiều social event. | FR-NOTI-003 | Should | P5 Discovery & Social | BN-P0-001,BN-P0-004,BN-P0-007 | Preference scheduler + push/email/in-app delivery pipeline | Notification center/preferences/deep-link UI | notification/preference/delivery log schema |  | Test functional path + negative/authorization cases for FR-NOTI-003 | Frequency user-configurable. | 5 | Not Started | Unassigned
BN-P6-082 | Subscription & Monetization | FR-PAY-001 | Với vai trò subscriber, tôi cần free/Premium entitlement theo feature/quota; server-side enforcement. | FR-PAY-001 | Must | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, account + entitlement | Billing adapters, entitlement, webhook reconciliation | Paywall/plans/receipt/manage-subscription UI | subscription/entitlement/transaction/webhook schema |  | Test functional path + negative/authorization cases for FR-PAY-001 | Không dựa UI-only gate. | 8 | Not Started | Unassigned
BN-P6-083 | Subscription & Monetization | FR-PAY-002 | Với vai trò subscriber, tôi cần hỗ trợ App Store/Google Play billing và web payment; xử lý renew/cancel/grace/refund. | FR-PAY-002 | Must | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, account + entitlement | Billing adapters, entitlement, webhook reconciliation | Paywall/plans/receipt/manage-subscription UI | subscription/entitlement/transaction/webhook schema |  | Test functional path + negative/authorization cases for FR-PAY-002 | Ledger idempotent. | 8 | Not Started | Unassigned
BN-P6-084 | Subscription & Monetization | FR-PAY-003 | Với vai trò subscriber, tôi cần family plan, promo code, trial, gift và grandfathering policy. | FR-PAY-003 | Should | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, account + entitlement | Billing adapters, entitlement, webhook reconciliation | Paywall/plans/receipt/manage-subscription UI | subscription/entitlement/transaction/webhook schema |  | Test functional path + negative/authorization cases for FR-PAY-003 | Không mất entitlement khi provider webhook trễ. | 5 | Not Started | Unassigned
BN-P6-085 | Subscription & Monetization | FR-PAY-004 | Với vai trò subscriber, tôi cần ads/affiliate nếu dùng phải được tách rõ, không gây ảnh hưởng safety/recommendation không khai báo. | FR-PAY-004 | Could | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, account + entitlement | Billing adapters, entitlement, webhook reconciliation | Paywall/plans/receipt/manage-subscription UI | subscription/entitlement/transaction/webhook schema |  | Test functional path + negative/authorization cases for FR-PAY-004 | Premium có thể ad-free. | 3 | Not Started | Unassigned
BN-P6-086 | Subscription & Monetization | FR-PAY-005 | Với vai trò subscriber, tôi cần paywall experiment qua feature flag/experiment nhưng tuân thủ consent và pricing transparency. | FR-PAY-005 | Should | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, account + entitlement | Billing adapters, entitlement, webhook reconciliation | Paywall/plans/receipt/manage-subscription UI | subscription/entitlement/transaction/webhook schema |  | Test functional path + negative/authorization cases for FR-PAY-005 | Audit experiment assignment. | 5 | Not Started | Unassigned
BN-P6-087 | Admin & CMS | FR-ADM-001 | Với vai trò admin, tôi cần admin RBAC cho content, moderation, support, billing, analytics, feature flag. | FR-ADM-001 | Must | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, admin auth | RBAC, CMS, feature flag, admin audit services | Admin/CMS/moderation/feature-flag dashboards | admin role/audit/CMS workflow schema |  | Test functional path + negative/authorization cases for FR-ADM-001 | Least privilege + audit log. | 5 | Not Started | Unassigned
BN-P6-088 | Admin & CMS | FR-ADM-002 | Với vai trò admin, tôi cần cMS quản lý recipe, ingredient canonical, taxonomy, regional variants, seasonal collections. | FR-ADM-002 | Must | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, admin auth | RBAC, CMS, feature flag, admin audit services | Admin/CMS/moderation/feature-flag dashboards | admin role/audit/CMS workflow schema |  | Test functional path + negative/authorization cases for FR-ADM-002 | Draft/review/approve/publish workflow. | 5 | Not Started | Unassigned
BN-P6-089 | Admin & CMS | FR-ADM-003 | Với vai trò admin, tôi cần dashboard theo dõi user, retention, content quality, error, moderation queue và revenue aggregate. | FR-ADM-003 | Must | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, admin auth | RBAC, CMS, feature flag, admin audit services | Admin/CMS/moderation/feature-flag dashboards | admin role/audit/CMS workflow schema |  | Test functional path + negative/authorization cases for FR-ADM-003 | Không expose secret/PII không cần thiết. | 5 | Not Started | Unassigned
BN-P6-090 | Admin & CMS | FR-ADM-004 | Với vai trò admin, tôi cần feature flag và remote config theo cohort/platform/version. | FR-ADM-004 | Must | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, admin auth | RBAC, CMS, feature flag, admin audit services | Admin/CMS/moderation/feature-flag dashboards | admin role/audit/CMS workflow schema |  | Test functional path + negative/authorization cases for FR-ADM-004 | Kill switch cho AI/social/billing feature. | 5 | Not Started | Unassigned
BN-P6-091 | Admin & CMS | FR-ADM-005 | Với vai trò admin, tôi cần support console tra cứu user theo masked identifier, entitlement, sync issue, report history. | FR-ADM-005 | Should | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, admin auth | RBAC, CMS, feature flag, admin audit services | Admin/CMS/moderation/feature-flag dashboards | admin role/audit/CMS workflow schema |  | Test functional path + negative/authorization cases for FR-ADM-005 | Sensitive action cần reason/audit. | 5 | Not Started | Unassigned
BN-P6-092 | Trust, Safety & Moderation | FR-MOD-001 | Với vai trò moderator/user, tôi cần user report post/comment/profile/recipe; category spam, abuse, unsafe food advice, copyright, impersonation. | FR-MOD-001 | Must | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, admin auth | Screening queue, review, action, appeal services | Report/block/mute/appeal/moderation console UI | moderation case/evidence/decision/appeal schema |  | Test functional path + negative/authorization cases for FR-MOD-001 | SLA và queue priority. | 8 | Not Started | Unassigned
BN-P6-093 | Trust, Safety & Moderation | FR-MOD-002 | Với vai trò moderator/user, tôi cần kết hợp automated screening + human review + appeal. | FR-MOD-002 | Must | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, admin auth | Screening queue, review, action, appeal services | Report/block/mute/appeal/moderation console UI | moderation case/evidence/decision/appeal schema |  | Test functional path + negative/authorization cases for FR-MOD-002 | Không auto-ban chỉ từ low-confidence AI. | 8 | Not Started | Unassigned
BN-P6-094 | Trust, Safety & Moderation | FR-MOD-003 | Với vai trò moderator/user, tôi cần food safety warning cho nguyên liệu sống, bảo quản, reheating và dị ứng. | FR-MOD-003 | Must | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, admin auth | Screening queue, review, action, appeal services | Report/block/mute/appeal/moderation console UI | moderation case/evidence/decision/appeal schema |  | Test functional path + negative/authorization cases for FR-MOD-003 | Không thay thế tư vấn y tế. | 8 | Not Started | Unassigned
BN-P6-095 | Trust, Safety & Moderation | FR-MOD-004 | Với vai trò moderator/user, tôi cần block/mute user, comment controls, hidden words. | FR-MOD-004 | Should | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, admin auth | Screening queue, review, action, appeal services | Report/block/mute/appeal/moderation console UI | moderation case/evidence/decision/appeal schema |  | Test functional path + negative/authorization cases for FR-MOD-004 | Áp dụng tức thì trên feed. | 5 | Not Started | Unassigned
BN-P6-096 | Trust, Safety & Moderation | FR-MOD-005 | Với vai trò moderator/user, tôi cần copyright/attribution takedown workflow cho recipe/media. | FR-MOD-005 | Should | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, admin auth | Screening queue, review, action, appeal services | Report/block/mute/appeal/moderation console UI | moderation case/evidence/decision/appeal schema |  | Test functional path + negative/authorization cases for FR-MOD-005 | Giữ evidence/audit theo policy. | 5 | Not Started | Unassigned
BN-P6-097 | Analytics & Experimentation | FR-AN-001 | Với vai trò product team, tôi cần event tracking chuẩn hóa cho acquisition → activation → cook → feedback → retention → conversion. | FR-AN-001 | Must | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, admin auth | Event ingestion, experiment assignment, KPI aggregation | Analytics consent/experiment surface + internal dashboards | analytics event/experiment/assignment schema |  | Test functional path + negative/authorization cases for FR-AN-001 | Event schema versioned. | 5 | Not Started | Unassigned
BN-P6-098 | Analytics & Experimentation | FR-AN-002 | Với vai trò product team, tôi cần a/B testing, feature rollout, holdout và experiment guardrail metrics. | FR-AN-002 | Should | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, admin auth | Event ingestion, experiment assignment, KPI aggregation | Analytics consent/experiment surface + internal dashboards | analytics event/experiment/assignment schema |  | Test functional path + negative/authorization cases for FR-AN-002 | Không experiment safety-critical logic. | 5 | Not Started | Unassigned
BN-P6-099 | Analytics & Experimentation | FR-AN-003 | Với vai trò product team, tôi cần referral code/link và reward theo policy chống abuse. | FR-AN-003 | Could | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, admin auth | Event ingestion, experiment assignment, KPI aggregation | Analytics consent/experiment surface + internal dashboards | analytics event/experiment/assignment schema |  | Test functional path + negative/authorization cases for FR-AN-003 | Fraud detection basic. | 3 | Not Started | Unassigned
BN-P6-100 | Analytics & Experimentation | FR-AN-004 | Với vai trò product team, tôi cần attribution campaign/channel và deep link. | FR-AN-004 | Should | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, admin auth | Event ingestion, experiment assignment, KPI aggregation | Analytics consent/experiment surface + internal dashboards | analytics event/experiment/assignment schema |  | Test functional path + negative/authorization cases for FR-AN-004 | Respect privacy/consent. | 5 | Not Started | Unassigned
BN-P6-101 | Analytics & Experimentation | FR-AN-005 | Với vai trò product team, tôi cần cohort dashboard theo lifecycle, Taste maturity và household adoption. | FR-AN-005 | Must | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, admin auth | Event ingestion, experiment assignment, KPI aggregation | Analytics consent/experiment surface + internal dashboards | analytics event/experiment/assignment schema |  | Test functional path + negative/authorization cases for FR-AN-005 | Data aggregated/anonymized where possible. | 5 | Not Started | Unassigned
BN-P6-102 | Support & Product Quality | FR-SUP-001 | Với vai trò user/support, tôi cần in-app feedback/bug report đính kèm app version, screen context và log kỹ thuật đã scrub PII. | FR-SUP-001 | Must | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, admin auth | Feedback/bug/quality-report/support diagnostic APIs | Feedback/help/status/support/diagnostic UI | support ticket/quality report/diagnostic schema |  | Test functional path + negative/authorization cases for FR-SUP-001 | User xem trước attachment. | 5 | Not Started | Unassigned
BN-P6-103 | Support & Product Quality | FR-SUP-002 | Với vai trò user/support, tôi cần help center/FAQ/search và contact support. | FR-SUP-002 | Should | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, admin auth | Feedback/bug/quality-report/support diagnostic APIs | Feedback/help/status/support/diagnostic UI | support ticket/quality report/diagnostic schema |  | Test functional path + negative/authorization cases for FR-SUP-002 | CMS-manageable. | 5 | Not Started | Unassigned
BN-P6-104 | Support & Product Quality | FR-SUP-003 | Với vai trò user/support, tôi cần recipe quality report riêng cho định lượng sai, step thiếu, kết quả không đúng. | FR-SUP-003 | Must | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, admin auth | Feedback/bug/quality-report/support diagnostic APIs | Feedback/help/status/support/diagnostic UI | support ticket/quality report/diagnostic schema |  | Test functional path + negative/authorization cases for FR-SUP-003 | Tạo content review task. | 5 | Not Started | Unassigned
BN-P6-105 | Support & Product Quality | FR-SUP-004 | Với vai trò user/support, tôi cần status page / maintenance message khi service suy giảm. | FR-SUP-004 | Should | P6 Business & Growth | BN-P0-001,BN-P0-004,BN-P0-007, admin auth | Feedback/bug/quality-report/support diagnostic APIs | Feedback/help/status/support/diagnostic UI | support ticket/quality report/diagnostic schema |  | Test functional path + negative/authorization cases for FR-SUP-004 | Remote config hỗ trợ. | 5 | Not Started | Unassigned
BN-P7-106 | Platform & Accessibility | FR-PLAT-001 | Với vai trò user, tôi cần web responsive/PWA và native iOS/Android cùng account/data. | FR-PLAT-001 | Must | P7 Production & Native | BN-P0-001,BN-P0-004,BN-P0-007, cross-cutting | Version/deep-link/i18n/unit-conversion/platform APIs | Responsive/PWA/native parity/a11y/i18n/deep-link UI | device/app-version/localization metadata schema |  | Test functional path + negative/authorization cases for FR-PLAT-001 | Core flows parity; platform-native billing/push. | 8 | Not Started | Unassigned
BN-P7-107 | Platform & Accessibility | FR-PLAT-002 | Với vai trò user, tôi cần hỗ trợ Vietnamese-first; kiến trúc i18n cho English và locale khác. | FR-PLAT-002 | Must | P7 Production & Native | BN-P0-001,BN-P0-004,BN-P0-007, cross-cutting | Version/deep-link/i18n/unit-conversion/platform APIs | Responsive/PWA/native parity/a11y/i18n/deep-link UI | device/app-version/localization metadata schema |  | Test functional path + negative/authorization cases for FR-PLAT-002 | Không hard-code copy trong logic. | 8 | Not Started | Unassigned
BN-P7-108 | Platform & Accessibility | FR-PLAT-003 | Với vai trò user, tôi cần unit system configurable g/ml/tsp/tbsp/cup; canonical internal unit. | FR-PLAT-003 | Must | P7 Production & Native | BN-P0-001,BN-P0-004,BN-P0-007, cross-cutting | Version/deep-link/i18n/unit-conversion/platform APIs | Responsive/PWA/native parity/a11y/i18n/deep-link UI | device/app-version/localization metadata schema |  | Test functional path + negative/authorization cases for FR-PLAT-003 | Conversion có rounding policy. | 8 | Not Started | Unassigned
BN-P7-109 | Platform & Accessibility | FR-PLAT-004 | Với vai trò user, tôi cần accessibility: screen reader labels, contrast, scalable text, keyboard web, voice alternative. | FR-PLAT-004 | Must | P7 Production & Native | BN-P0-001,BN-P0-004,BN-P0-007, cross-cutting | Version/deep-link/i18n/unit-conversion/platform APIs | Responsive/PWA/native parity/a11y/i18n/deep-link UI | device/app-version/localization metadata schema |  | Test functional path + negative/authorization cases for FR-PLAT-004 | Theo WCAG 2.2 AA mục tiêu. | 8 | Not Started | Unassigned
BN-P7-110 | Platform & Accessibility | FR-PLAT-005 | Với vai trò user, tôi cần deep link/universal link và share card cho recipe/post/profile. | FR-PLAT-005 | Should | P7 Production & Native | BN-P0-001,BN-P0-004,BN-P0-007, cross-cutting | Version/deep-link/i18n/unit-conversion/platform APIs | Responsive/PWA/native parity/a11y/i18n/deep-link UI | device/app-version/localization metadata schema |  | Test functional path + negative/authorization cases for FR-PLAT-005 | Fallback web nếu app chưa cài. | 5 | Not Started | Unassigned
BN-P7-111 | Privacy & Data Control | FR-PRV-001 | Với vai trò user, tôi cần consent tách biệt cho personalization, analytics, marketing và social discovery khi cần. | FR-PRV-001 | Must | P7 Production & Native | BN-P0-001,BN-P0-004,BN-P0-007, cross-cutting | Consent/export/delete/anonymization workflows | Consent/privacy center/export/delete controls | consent/export/delete-request/privacy-audit schema |  | Test functional path + negative/authorization cases for FR-PRV-001 | Consent versioned. | 5 | Not Started | Unassigned
BN-P7-112 | Privacy & Data Control | FR-PRV-002 | Với vai trò user, tôi cần cho phép user xem/xóa cook history, feedback, media, social content và household membership. | FR-PRV-002 | Must | P7 Production & Native | BN-P0-001,BN-P0-004,BN-P0-007, cross-cutting | Consent/export/delete/anonymization workflows | Consent/privacy center/export/delete controls | consent/export/delete-request/privacy-audit schema |  | Test functional path + negative/authorization cases for FR-PRV-002 | Delete propagation có SLA. | 5 | Not Started | Unassigned
BN-P7-113 | Privacy & Data Control | FR-PRV-003 | Với vai trò user, tôi cần privacy mặc định: personal notes/private cook history không public. | FR-PRV-003 | Must | P7 Production & Native | BN-P0-001,BN-P0-004,BN-P0-007, cross-cutting | Consent/export/delete/anonymization workflows | Consent/privacy center/export/delete controls | consent/export/delete-request/privacy-audit schema |  | Test functional path + negative/authorization cases for FR-PRV-003 | Social publish phải explicit. | 5 | Not Started | Unassigned
BN-P7-114 | Privacy & Data Control | FR-PRV-004 | Với vai trò user, tôi cần minor/child profile không có social public độc lập nếu không phù hợp policy. | FR-PRV-004 | Must | P7 Production & Native | BN-P0-001,BN-P0-004,BN-P0-007, cross-cutting | Consent/export/delete/anonymization workflows | Consent/privacy center/export/delete controls | consent/export/delete-request/privacy-audit schema |  | Test functional path + negative/authorization cases for FR-PRV-004 | Household guardian control. | 5 | Not Started | Unassigned
BN-P7-115 | Privacy & Data Control | FR-PRV-005 | Với vai trò user, tôi cần data export ở định dạng machine-readable cho profile, recipe versions và history. | FR-PRV-005 | Should | P7 Production & Native | BN-P0-001,BN-P0-004,BN-P0-007, cross-cutting | Consent/export/delete/anonymization workflows | Consent/privacy center/export/delete controls | consent/export/delete-request/privacy-audit schema |  | Test functional path + negative/authorization cases for FR-PRV-005 | Không export secret/internal scores có risk abuse nếu không cần. | 5 | Not Started | Unassigned

## Release Plan
Phase | Goal | Key Deliverables | Entry Criteria | Exit / Quality Gate | Primary KPIs | Recommended Sequence
P0 Foundation | Tạo nền tảng code và delivery ổn định | Monorepo; local stack; CI/CD; API conventions; DB migration; observability; security; AI gateway; analytics schema | SRS/SDD baseline approved | Repo build green; dev stack reproducible; security/observability baselines; contract ready | Build success; test pass; setup time | 1
P1 Core Cooking | Hoàn thành vòng nấu món chuẩn end-to-end | Account; verified recipes; recipe detail; Cook Mode; timers; feedback; cooking memory | P0 passed | User đăng ký → chọn recipe → cook → feedback; không mất session; recipe data structured | Activation; first cook; feedback completion | 2
P2 Personalization | Chứng minh app học khẩu vị và cải thiện lần nấu sau | Taste DNA; recipe adjustments; versions/diff; My Best Version; scaling guardrails | P1 data loop available | Taste update traceable; adjustments bounded; version compare/rollback works | Accepted adjustment rate; repeat recipe score uplift | 3
P3 Household & Planning | Tối ưu bữa ăn cho gia đình và kế hoạch tuần/tháng | Household; Family Taste; meal planner; lock/regenerate; Vietnamese meal structure | P2 stable | Allergy hard constraints; family split instructions; planner satisfies locked constraints | Household adoption; plan reuse; conflict rate | 4
P4 Utility | Giảm lãng phí và tăng frequency sử dụng | Pantry; leftovers; shopping; budget; Rescue; substitutions | P3 planning ready | Inventory ledger consistent; rescue safe; shopping reflects pantry | Pantry usage; waste proxy; rescue success | 5
P5 Discovery & Social | Tạo growth loop và community có utility | Search; recommendations; Taste Match; feed; creator; fork; gamification; notifications | Core utility stable + moderation baseline | Feed/reco explainable; report/block works; social content traceable | Save→cook; taste-match follow; creator activation | 6
P6 Business & Growth | Bật doanh thu và vận hành quy mô sản phẩm | Subscription; entitlement; billing; admin/CMS; moderation; analytics; experiments; support | Retention signal established | Billing reconciles; entitlements server-side; admin audit; experiment guardrails | Paid conversion; churn; ARPPU; support SLA | 7
P7 Production & Native | Hoàn thiện production scale và app native | iOS/Android parity; privacy center; accessibility; performance; DR; store readiness | Business model validated | SLO/DR tests pass; privacy/export/delete; mobile store compliance | Crash-free; p95 latency; availability; store rating | 8

## Traceability
Requirement ID | Type | Domain | Requirement | Priority | Acceptance / Rule | Mapped Backlog ID | Coverage Status
FR-ACC-001 | FR | ACC | Đăng ký/đăng nhập bằng email, số điện thoại và social login; hỗ trợ guest mode giới hạn. | Must | Không tạo duplicate identity; có cơ chế link account. | BN-P1-001 | Mapped
FR-ACC-002 | FR | ACC | Onboarding thu thập mục tiêu nấu ăn, số người, vùng miền, mức kỹ năng, dụng cụ bếp, thời gian và budget. | Must | Có thể skip từng phần; chỉnh lại sau. | BN-P1-002 | Mapped
FR-ACC-003 | FR | ACC | Hồ sơ lưu ngôn ngữ, đơn vị đo, chế độ ăn, dị ứng, nguyên liệu tránh, lịch sử và privacy settings. | Must | Dị ứng được ưu tiên hơn mọi recommendation. | BN-P1-003 | Mapped
FR-ACC-004 | FR | ACC | Cho phép export dữ liệu, xóa tài khoản, vô hiệu hóa tài khoản và tải bản sao dữ liệu. | Must | Tuân thủ chính sách retention/erasure. | BN-P1-004 | Mapped
FR-ACC-005 | FR | ACC | Hỗ trợ nhiều thiết bị, đồng bộ session và revoke thiết bị. | Should | Hiển thị lịch sử đăng nhập bất thường. | BN-P1-005 | Mapped
FR-TASTE-001 | FR | TASTE | Duy trì Taste DNA theo nhiều chiều: mặn, ngọt, chua, cay, umami, béo, đắng, độ mềm/giòn, độ khô/nước, hành/tỏi, mùi thảo mộc. | Must | Mỗi dimension có score + confidence + sample count. | BN-P2-006 | Mapped
FR-TASTE-002 | FR | TASTE | Taste DNA phải học từ onboarding, rating, post-cook feedback, thao tác chỉnh recipe và hành vi lựa chọn. | Must | Nguồn tín hiệu có trọng số khác nhau. | BN-P2-007 | Mapped
FR-TASTE-003 | FR | TASTE | Cho phép preference toàn cục, theo nhóm món, theo nguyên liệu và theo recipe cụ thể. | Must | Context-specific preference override global. | BN-P2-008 | Mapped
FR-TASTE-004 | FR | TASTE | Hiển thị Taste DNA theo cách dễ hiểu và cho phép user chỉnh thủ công. | Should | Manual edit được audit và giảm confidence tạm thời. | BN-P2-009 | Mapped
FR-TASTE-005 | FR | TASTE | Cho phép reset một dimension hoặc toàn bộ Taste DNA mà không xóa lịch sử cook. | Could | Có cảnh báo hậu quả personalization. | BN-P2-010 | Mapped
FR-HH-001 | FR | HH | Tạo household, mời thành viên, guest profile và child profile. | Must | Role Owner/Admin/Member/Guest. | BN-P3-011 | Mapped
FR-HH-002 | FR | HH | Mỗi thành viên có Taste DNA, allergy/diet và serving size riêng. | Must | Không gộp dữ liệu cá nhân ngoài consent. | BN-P3-012 | Mapped
FR-HH-003 | FR | HH | Family Taste Engine đề xuất công thức dung hòa và hướng dẫn tách phần khi preference xung đột. | Must | Allergy luôn là hard constraint. | BN-P3-013 | Mapped
FR-HH-004 | FR | HH | Meal plan, pantry, shopping list có thể dùng chung household và đồng bộ real time. | Must | Conflict merge có versioning. | BN-P3-014 | Mapped
FR-HH-005 | FR | HH | Cho phép lưu “ai ăn bữa này” để recommendation theo đúng nhóm người. | Should | Có preset: cả nhà, hai người, trẻ em... | BN-P3-015 | Mapped
FR-REC-001 | FR | REC | Recipe lưu cấu trúc định lượng: ingredient canonical, quantity, unit, preparation, substitution, step, heat, duration, serving. | Must | Không dùng “vừa đủ” làm dữ liệu duy nhất cho gia vị chính. | BN-P1-016 | Mapped
FR-REC-002 | FR | REC | Phân loại món theo vùng miền, bữa ăn, kỹ thuật, nguyên liệu, mùa, độ khó, thời gian và chi phí. | Must | Taxonomy quản trị qua CMS. | BN-P1-017 | Mapped
FR-REC-003 | FR | REC | Mỗi recipe có source/provenance, reviewer, trạng thái draft/verified/published/deprecated. | Must | Verified recipe có lịch sử review. | BN-P1-018 | Mapped
FR-REC-004 | FR | REC | Hỗ trợ ảnh, video ngắn, step image, nutrition optional và equipment. | Should | Media có moderation/licensing metadata. | BN-P1-019 | Mapped
FR-REC-005 | FR | REC | Hỗ trợ biến thể Bắc/Trung/Nam/gia đình nhưng vẫn giữ lineage của món gốc. | Should | Không overwrite recipe verified gốc. | BN-P1-020 | Mapped
FR-REC-006 | FR | REC | Creator/user có thể submit recipe để review hoặc public theo policy. | Should | Nội dung community gắn nhãn nguồn rõ ràng. | BN-P1-021 | Mapped
FR-EVO-001 | FR | EVO | Sinh bản recipe cá nhân dựa trên Taste DNA, serving, household, diet, equipment và history. | Must | Luôn hiển thị các thay đổi so với bản chuẩn. | BN-P2-022 | Mapped
FR-EVO-002 | FR | EVO | Sau cook feedback, tạo version V2/V3... với diff định lượng, lý do và confidence. | Must | Không thay đổi silent; user có thể accept/reject. | BN-P2-023 | Mapped
FR-EVO-003 | FR | EVO | User có thể pin một version làm “My Best Version”, rollback hoặc compare 2 versions. | Must | Lineage không bị mất. | BN-P2-024 | Mapped
FR-EVO-004 | FR | EVO | Recipe Fork: fork recipe của creator/user khác thành nhánh riêng và giữ attribution. | Should | Có source chain và license rules. | BN-P2-025 | Mapped
FR-EVO-005 | FR | EVO | Tự động scale recipe theo serving nhưng giữ ratio/constraint đặc thù. | Must | Có rounding rule theo unit/ingredient. | BN-P2-026 | Mapped
FR-EVO-006 | FR | EVO | Không tự thay đổi ingredient liên quan dị ứng/an toàn nếu không có xác nhận. | Must | Safety constraint hard-coded. | BN-P2-027 | Mapped
FR-COOK-001 | FR | COOK | Cook Mode hiển thị từng bước lớn, ingredient tại bước, timer, nhiệt độ và progress. | Must | Screen-awake optional; font lớn. | BN-P1-028 | Mapped
FR-COOK-002 | FR | COOK | Voice/hands-free command: tiếp theo, quay lại, đặt timer, đọc lại, còn bao lâu, đổi khẩu phần. | Should | Không yêu cầu chạm màn hình trong luồng chính. | BN-P1-029 | Mapped
FR-COOK-003 | FR | COOK | Hỗ trợ nhiều timer đồng thời, background notification và resume session. | Must | Không mất timer khi app background/crash. | BN-P1-030 | Mapped
FR-COOK-004 | FR | COOK | Cho phép log thay thế nguyên liệu, quantity thực tế, thời gian thực tế và deviation ngay khi nấu. | Should | Dữ liệu dùng cho diagnosis/learning. | BN-P1-031 | Mapped
FR-COOK-005 | FR | COOK | Offline cooking cache cho recipe đã mở/lưu. | Should | Feedback sync lại khi có mạng. | BN-P1-032 | Mapped
FR-COOK-006 | FR | COOK | Camera optional để ghi ảnh trước/sau và gắn vào cook history. | Could | Media privacy mặc định private. | BN-P1-033 | Mapped
FR-FB-001 | FR | FB | Feedback nhanh sau bữa: mặn/ngọt/chua/cay/béo/texture/nước + overall score. | Must | Hoàn thành <= 10 giây. | BN-P1-034 | Mapped
FR-FB-002 | FR | FB | Cho phép free-text note, voice note và ghi chú riêng tư. | Should | Private by default. | BN-P1-035 | Mapped
FR-FB-003 | FR | FB | Cooking Memory lưu thời gian, household members, actual ingredients, feedback và ảnh. | Must | Có timeline theo món/ngày. | BN-P1-036 | Mapped
FR-FB-004 | FR | FB | App phát hiện feedback mâu thuẫn/thiếu dữ liệu và hỏi follow-up tối thiểu. | Should | Không gây fatigue. | BN-P1-037 | Mapped
FR-FB-005 | FR | FB | User có thể sửa feedback cũ; engine re-compute ảnh hưởng khi cần. | Should | Audit revision retained. | BN-P1-038 | Mapped
FR-MEAL-001 | FR | MEAL | Sinh meal plan ngày/tuần/tháng theo household, budget, time, pantry, preference và lịch sử. | Must | Có regenerate từng bữa hoặc toàn plan. | BN-P3-039 | Mapped
FR-MEAL-002 | FR | MEAL | Hiểu cấu trúc mâm cơm Việt: cơm + món mặn + rau + canh + món phụ/nước chấm. | Must | Tránh xung đột hương vị/kỹ thuật quá giống. | BN-P3-040 | Mapped
FR-MEAL-003 | FR | MEAL | Cho phép khóa món/bữa/ngày và regenerate phần còn lại. | Must | Khóa không bị engine overwrite. | BN-P3-041 | Mapped
FR-MEAL-004 | FR | MEAL | Tối ưu tái sử dụng nguyên liệu giữa các ngày để giảm lãng phí và số lần đi chợ. | Must | Có explanation về reuse. | BN-P3-042 | Mapped
FR-MEAL-005 | FR | MEAL | Calendar view, drag-drop, meal template, recurring plan, ăn ngoài/skipped meal. | Should | Không tính shopping cho bữa ăn ngoài. | BN-P3-043 | Mapped
FR-MEAL-006 | FR | MEAL | Theo dõi estimate cost, prep time, cooking load và diversity. | Should | Cost source có timestamp/region. | BN-P3-044 | Mapped
FR-PAN-001 | FR | PAN | Pantry lưu ingredient, quantity, unit, purchase/open/expiry date, location và household owner. | Must | Hỗ trợ manual + barcode/receipt/image optional. | BN-P4-045 | Mapped
FR-PAN-002 | FR | PAN | Trừ tồn kho từ cook session và cho phép confirm/edit trước khi commit. | Must | Không âm tồn kho silent. | BN-P4-046 | Mapped
FR-PAN-003 | FR | PAN | Cảnh báo nguyên liệu sắp hết hạn và ưu tiên recommendation sử dụng trước. | Must | User cấu hình threshold. | BN-P4-047 | Mapped
FR-PAN-004 | FR | PAN | Leftover object lưu món còn lại, quantity, ngày nấu, storage và use-by. | Should | Gợi ý reheat/transform an toàn. | BN-P4-048 | Mapped
FR-PAN-005 | FR | PAN | “Nấu từ những gì đang có” lọc món theo coverage pantry và missing ingredients. | Must | Hiển thị % coverage và món cần mua thêm. | BN-P4-049 | Mapped
FR-PAN-006 | FR | PAN | Hỗ trợ household stock reconciliation và inventory adjustment log. | Could | Phục vụ user dùng thường xuyên. | BN-P4-050 | Mapped
FR-SHOP-001 | FR | SHOP | Sinh shopping list từ meal plan/pantry, merge ingredient theo canonical unit. | Must | Trừ tồn kho khả dụng. | BN-P4-051 | Mapped
FR-SHOP-002 | FR | SHOP | Chia list theo nhóm hàng/chợ/siêu thị và người phụ trách. | Should | Real-time shared check-off. | BN-P4-052 | Mapped
FR-SHOP-003 | FR | SHOP | Cho phép budget mục tiêu theo tuần/tháng và cảnh báo plan vượt budget. | Must | Recommendation đề xuất thay món/nguyên liệu. | BN-P4-053 | Mapped
FR-SHOP-004 | FR | SHOP | Theo dõi actual spend và học mức giá user nhập để ước tính tốt hơn. | Should | Không giả định giá realtime khi không có nguồn. | BN-P4-054 | Mapped
FR-SHOP-005 | FR | SHOP | Affiliate/deep link mua nguyên liệu là optional và phải phân biệt rõ nội dung tài trợ. | Could | Không ảnh hưởng ranking nếu không khai báo. | BN-P4-055 | Mapped
FR-RES-001 | FR | RES | Rescue Mode cho các lỗi: mặn, nhạt, ngọt, chua, cay, loãng, đặc, cháy nhẹ, sống/dai, tanh. | Must | Hỏi context tối thiểu trước khi hướng dẫn. | BN-P4-056 | Mapped
FR-RES-002 | FR | RES | Đưa hướng dẫn cứu món theo lượng thực tế, không chỉ lời khuyên chung. | Must | Có risk warning khi không thể cứu an toàn. | BN-P4-057 | Mapped
FR-RES-003 | FR | RES | Smart substitution đề xuất thay thế theo chức năng ingredient, taste impact, allergy và pantry. | Must | Hiển thị mức độ tương đương. | BN-P4-058 | Mapped
FR-RES-004 | FR | RES | Sau rescue, cho phép user báo kết quả để engine cải thiện recommendation. | Should | Không cập nhật taste preference từ lỗi kỹ thuật một cách trực tiếp. | BN-P4-059 | Mapped
FR-SRCH-001 | FR | SRCH | Search theo tên, ingredient, vùng miền, thời gian, budget, equipment, diet, skill, pantry coverage. | Must | Faceted filtering + typo tolerant. | BN-P5-060 | Mapped
FR-SRCH-002 | FR | SRCH | Home recommendation kết hợp Taste DNA, household, recent meals, season, pantry, trend và exploration. | Must | Có explanation “vì sao bạn thấy món này”. | BN-P5-061 | Mapped
FR-SRCH-003 | FR | SRCH | Không lặp món quá dày và tránh filter bubble bằng exploration có kiểm soát. | Should | Diversity constraints configurable. | BN-P5-062 | Mapped
FR-SRCH-004 | FR | SRCH | Recommendation phải xử lý cold-start và anonymous user. | Must | Fallback editorial/popular/seasonal. | BN-P5-063 | Mapped
FR-SRCH-005 | FR | SRCH | User có thể dislike/not interested và hide creator/tag. | Should | Feedback tác động ranking ngay. | BN-P5-064 | Mapped
FR-SOC-001 | FR | SOC | Feed cho phép post ảnh/video món, recipe reference, cook result, tip, câu hỏi và story ngắn. | Should | Privacy public/follower/household/private. | BN-P5-065 | Mapped
FR-SOC-002 | FR | SOC | Follow user/creator/topic/recipe; like/save/comment/share/report. | Should | Anti-spam/rate limit. | BN-P5-066 | Mapped
FR-SOC-003 | FR | SOC | Taste Match tính độ tương đồng khẩu vị và dùng để xếp hạng review/recipe. | Should | Không công khai vector raw nếu user không opt-in. | BN-P5-067 | Mapped
FR-SOC-004 | FR | SOC | Hiển thị “người có khẩu vị giống bạn” và recipe được họ đánh giá cao. | Should | Có block/hide. | BN-P5-068 | Mapped
FR-SOC-005 | FR | SOC | Recipe Fork/Remix hiển thị cây lineage, attribution và popularity của nhánh. | Should | Original creator nhận attribution. | BN-P5-069 | Mapped
FR-SOC-006 | FR | SOC | Challenge theo tuần/tháng: nấu 3 món rau, món vùng miền, zero-waste... | Could | Không dùng dark pattern gây nghiện. | BN-P5-070 | Mapped
FR-SOC-007 | FR | SOC | DM/Group chat không bắt buộc ở release đầu nhưng kiến trúc phải không cản trở mở rộng. | Could | Nếu triển khai cần abuse controls riêng. | BN-P5-071 | Mapped
FR-CRT-001 | FR | CRT | Creator profile có bio, specialty, verified badge, recipe collection, followers và analytics. | Should | Verification workflow qua Admin. | BN-P5-072 | Mapped
FR-CRT-002 | FR | CRT | Creator Studio hỗ trợ draft, version, schedule publish, media, ingredient structured editor. | Should | Recipe validation trước publish. | BN-P5-073 | Mapped
FR-CRT-003 | FR | CRT | Creator xem analytics aggregate: views, saves, cooks, success feedback, fork count. | Should | Không tiết lộ dữ liệu cá nhân user. | BN-P5-074 | Mapped
FR-CRT-004 | FR | CRT | Hỗ trợ revenue share/paid collection trong tương lai qua entitlement. | Could | Tách khỏi core subscription ledger. | BN-P5-075 | Mapped
FR-GAME-001 | FR | GAME | Streak, cooking milestone, badge và collection phải phản ánh giá trị thực, không ép engagement. | Could | Cho phép tắt gamification. | BN-P5-076 | Mapped
FR-GAME-002 | FR | GAME | Weekly recap: món đã nấu, tiết kiệm, ingredient dùng hết, taste learning mới. | Should | Có opt-out. | BN-P5-077 | Mapped
FR-GAME-003 | FR | GAME | Seasonal missions/challenges được CMS cấu hình. | Could | Moderation cho user-generated challenge nếu có. | BN-P5-078 | Mapped
FR-NOTI-001 | FR | NOTI | Push/in-app/email cho meal reminder, pantry expiry, shared list change, comment/follow, billing và system notice. | Must | User chọn channel/topic/quiet hours. | BN-P5-079 | Mapped
FR-NOTI-002 | FR | NOTI | Notification phải deep-link đúng context và deduplicate. | Must | Có inbox trạng thái read/unread. | BN-P5-080 | Mapped
FR-NOTI-003 | FR | NOTI | Digest thay cho spam khi nhiều social event. | Should | Frequency user-configurable. | BN-P5-081 | Mapped
FR-PAY-001 | FR | PAY | Free/Premium entitlement theo feature/quota; server-side enforcement. | Must | Không dựa UI-only gate. | BN-P6-082 | Mapped
FR-PAY-002 | FR | PAY | Hỗ trợ App Store/Google Play billing và web payment; xử lý renew/cancel/grace/refund. | Must | Ledger idempotent. | BN-P6-083 | Mapped
FR-PAY-003 | FR | PAY | Family plan, promo code, trial, gift và grandfathering policy. | Should | Không mất entitlement khi provider webhook trễ. | BN-P6-084 | Mapped
FR-PAY-004 | FR | PAY | Ads/affiliate nếu dùng phải được tách rõ, không gây ảnh hưởng safety/recommendation không khai báo. | Could | Premium có thể ad-free. | BN-P6-085 | Mapped
FR-PAY-005 | FR | PAY | Paywall experiment qua feature flag/experiment nhưng tuân thủ consent và pricing transparency. | Should | Audit experiment assignment. | BN-P6-086 | Mapped
FR-ADM-001 | FR | ADM | Admin RBAC cho content, moderation, support, billing, analytics, feature flag. | Must | Least privilege + audit log. | BN-P6-087 | Mapped
FR-ADM-002 | FR | ADM | CMS quản lý recipe, ingredient canonical, taxonomy, regional variants, seasonal collections. | Must | Draft/review/approve/publish workflow. | BN-P6-088 | Mapped
FR-ADM-003 | FR | ADM | Dashboard theo dõi user, retention, content quality, error, moderation queue và revenue aggregate. | Must | Không expose secret/PII không cần thiết. | BN-P6-089 | Mapped
FR-ADM-004 | FR | ADM | Feature flag và remote config theo cohort/platform/version. | Must | Kill switch cho AI/social/billing feature. | BN-P6-090 | Mapped
FR-ADM-005 | FR | ADM | Support console tra cứu user theo masked identifier, entitlement, sync issue, report history. | Should | Sensitive action cần reason/audit. | BN-P6-091 | Mapped
FR-MOD-001 | FR | MOD | User report post/comment/profile/recipe; category spam, abuse, unsafe food advice, copyright, impersonation. | Must | SLA và queue priority. | BN-P6-092 | Mapped
FR-MOD-002 | FR | MOD | Kết hợp automated screening + human review + appeal. | Must | Không auto-ban chỉ từ low-confidence AI. | BN-P6-093 | Mapped
FR-MOD-003 | FR | MOD | Food safety warning cho nguyên liệu sống, bảo quản, reheating và dị ứng. | Must | Không thay thế tư vấn y tế. | BN-P6-094 | Mapped
FR-MOD-004 | FR | MOD | Block/mute user, comment controls, hidden words. | Should | Áp dụng tức thì trên feed. | BN-P6-095 | Mapped
FR-MOD-005 | FR | MOD | Copyright/attribution takedown workflow cho recipe/media. | Should | Giữ evidence/audit theo policy. | BN-P6-096 | Mapped
FR-AN-001 | FR | AN | Event tracking chuẩn hóa cho acquisition → activation → cook → feedback → retention → conversion. | Must | Event schema versioned. | BN-P6-097 | Mapped
FR-AN-002 | FR | AN | A/B testing, feature rollout, holdout và experiment guardrail metrics. | Should | Không experiment safety-critical logic. | BN-P6-098 | Mapped
FR-AN-003 | FR | AN | Referral code/link và reward theo policy chống abuse. | Could | Fraud detection basic. | BN-P6-099 | Mapped
FR-AN-004 | FR | AN | Attribution campaign/channel và deep link. | Should | Respect privacy/consent. | BN-P6-100 | Mapped
FR-AN-005 | FR | AN | Cohort dashboard theo lifecycle, Taste maturity và household adoption. | Must | Data aggregated/anonymized where possible. | BN-P6-101 | Mapped
FR-SUP-001 | FR | SUP | In-app feedback/bug report đính kèm app version, screen context và log kỹ thuật đã scrub PII. | Must | User xem trước attachment. | BN-P6-102 | Mapped
FR-SUP-002 | FR | SUP | Help center/FAQ/search và contact support. | Should | CMS-manageable. | BN-P6-103 | Mapped
FR-SUP-003 | FR | SUP | Recipe quality report riêng cho định lượng sai, step thiếu, kết quả không đúng. | Must | Tạo content review task. | BN-P6-104 | Mapped
FR-SUP-004 | FR | SUP | Status page / maintenance message khi service suy giảm. | Should | Remote config hỗ trợ. | BN-P6-105 | Mapped
FR-PLAT-001 | FR | PLAT | Web responsive/PWA và native iOS/Android cùng account/data. | Must | Core flows parity; platform-native billing/push. | BN-P7-106 | Mapped
FR-PLAT-002 | FR | PLAT | Hỗ trợ Vietnamese-first; kiến trúc i18n cho English và locale khác. | Must | Không hard-code copy trong logic. | BN-P7-107 | Mapped
FR-PLAT-003 | FR | PLAT | Unit system configurable g/ml/tsp/tbsp/cup; canonical internal unit. | Must | Conversion có rounding policy. | BN-P7-108 | Mapped
FR-PLAT-004 | FR | PLAT | Accessibility: screen reader labels, contrast, scalable text, keyboard web, voice alternative. | Must | Theo WCAG 2.2 AA mục tiêu. | BN-P7-109 | Mapped
FR-PLAT-005 | FR | PLAT | Deep link/universal link và share card cho recipe/post/profile. | Should | Fallback web nếu app chưa cài. | BN-P7-110 | Mapped
FR-PRV-001 | FR | PRV | Consent tách biệt cho personalization, analytics, marketing và social discovery khi cần. | Must | Consent versioned. | BN-P7-111 | Mapped
FR-PRV-002 | FR | PRV | Cho phép user xem/xóa cook history, feedback, media, social content và household membership. | Must | Delete propagation có SLA. | BN-P7-112 | Mapped
FR-PRV-003 | FR | PRV | Privacy mặc định: personal notes/private cook history không public. | Must | Social publish phải explicit. | BN-P7-113 | Mapped
FR-PRV-004 | FR | PRV | Minor/child profile không có social public độc lập nếu không phù hợp policy. | Must | Household guardian control. | BN-P7-114 | Mapped
FR-PRV-005 | FR | PRV | Data export ở định dạng machine-readable cho profile, recipe versions và history. | Should | Không export secret/internal scores có risk abuse nếu không cần. | BN-P7-115 | Mapped
BR-001 | BR | 001 | Dị ứng và restriction an toàn là hard constraint, ưu tiên hơn taste, trend, monetization và creator ranking. |  |  | Mapped during feature implementation | Mapped
BR-002 | BR | 002 | Mọi điều chỉnh recipe cá nhân phải trace được về recipe/version nguồn và lý do. |  |  | Mapped during feature implementation | Mapped
BR-003 | BR | 003 | AI không được tự tạo khẳng định an toàn thực phẩm khi không có rule/source nội bộ phù hợp. |  |  | Mapped during feature implementation | Mapped
BR-004 | BR | 004 | User feedback về “mặn/ngọt...” chỉ cập nhật Taste DNA khi không bị đánh dấu là lỗi kỹ thuật/rescue bất thường. |  |  | Mapped during feature implementation | Mapped
BR-005 | BR | 005 | Taste DNA có confidence; signal ít dữ liệu không được áp adjustment lớn. |  |  | Mapped during feature implementation | Mapped
BR-006 | BR | 006 | Manual preference do user chỉnh có độ ưu tiên cao nhưng có thể được user reset. |  |  | Mapped during feature implementation | Mapped
BR-007 | BR | 007 | Household recommendation phải thỏa tất cả allergy/restriction của người tham gia bữa ăn. |  |  | Mapped during feature implementation | Mapped
BR-008 | BR | 008 | Recipe verified không bị community edit trực tiếp; mọi thay đổi là version/fork mới. |  |  | Mapped during feature implementation | Mapped
BR-009 | BR | 009 | Attribution của recipe fork phải được giữ xuyên suốt lineage. |  |  | Mapped during feature implementation | Mapped
BR-010 | BR | 010 | Personal cook note mặc định private. |  |  | Mapped during feature implementation | Mapped
BR-011 | BR | 011 | Social post không tự public ảnh từ cook session. |  |  | Mapped during feature implementation | Mapped
BR-012 | BR | 012 | Meal plan không tự đưa shopping item cho meal đánh dấu eating-out/skipped. |  |  | Mapped during feature implementation | Mapped
BR-013 | BR | 013 | Pantry deduction phải có khả năng undo và audit. |  |  | Mapped during feature implementation | Mapped
BR-014 | BR | 014 | Không cho phép inventory quantity âm nếu không có adjustment explícit. |  |  | Mapped during feature implementation | Mapped
BR-015 | BR | 015 | Premium entitlement xác thực server-side và idempotent theo transaction provider. |  |  | Mapped during feature implementation | Mapped
BR-016 | BR | 016 | Paid/affiliate content phải gắn nhãn rõ và không vượt safety constraints. |  |  | Mapped during feature implementation | Mapped
BR-017 | BR | 017 | Recommendation phải hỗ trợ “Why this?” và “Not interested”. |  |  | Mapped during feature implementation | Mapped
BR-018 | BR | 018 | Content moderation decision quan trọng phải có audit và appeal channel. |  |  | Mapped during feature implementation | Mapped
BR-019 | BR | 019 | Feature flag có thể vô hiệu hóa nhanh AI generation, social posting, payment hoặc notification khi có sự cố. |  |  | Mapped during feature implementation | Mapped
BR-020 | BR | 020 | Dữ liệu taste/social của child profile không dùng cho public discovery khi không có policy/consent phù hợp. |  |  | Mapped during feature implementation | Mapped
BR-021 | BR | 021 | Giá/chi phí chỉ được gắn timestamp/nguồn; nếu là estimate phải ghi rõ. |  |  | Mapped during feature implementation | Mapped
BR-022 | BR | 022 | Nutrition/health output nếu có chỉ mang tính thông tin và không thay thế tư vấn y tế. |  |  | Mapped during feature implementation | Mapped
BR-023 | BR | 023 | User có quyền rollback recipe personal version nhưng hệ thống giữ audit history. |  |  | Mapped during feature implementation | Mapped
BR-024 | BR | 024 | Delete account phải vô hiệu hóa truy cập ngay và hoàn tất purge/anonymize theo retention policy. |  |  | Mapped during feature implementation | Mapped
BR-025 | BR | 025 | Experiment không được thay đổi safety constraint, allergy handling hoặc consent semantics. |  |  | Mapped during feature implementation | Mapped
BR-026 | BR | 026 | Taste Match chỉ public ở dạng score/label khi cả hai phía và policy cho phép; vector raw không public. |  |  | Mapped during feature implementation | Mapped
BR-027 | BR | 027 | Creator analytics chỉ cung cấp aggregate, không expose danh tính người nấu nếu không có consent. |  |  | Mapped during feature implementation | Mapped
BR-028 | BR | 028 | Search/recommendation phải xử lý content deprecated/unsafe bằng cách loại khỏi candidate set. |  |  | Mapped during feature implementation | Mapped
BR-029 | BR | 029 | Recipe scale không linear mù quáng với toàn bộ gia vị/kỹ thuật; ingredient có scaling rule riêng. |  |  | Mapped during feature implementation | Mapped
BR-030 | BR | 030 | App không hứa “cứu” món nếu tình trạng liên quan an toàn (hỏng, ôi, sống nguy hiểm); phải khuyến nghị bỏ khi cần. |  |  | Mapped during feature implementation | Mapped
AI-001 | AI | 001 | LLM chỉ là lớp hỗ trợ giải thích/generation; structured recipe truth nằm trong domain data. |  |  | BN-P0-011 | Mapped
AI-002 | AI | 002 | Taste adjustment phải có deterministic guardrail về range, allergy, scaling và ingredient compatibility. |  |  | BN-P0-011 | Mapped
AI-003 | AI | 003 | Recommendation phải trả explanation factors; user có thể dislike/hide. |  |  | BN-P0-011 | Mapped
AI-004 | AI | 004 | Mỗi model/prompt/config phải versioned để audit và A/B test. |  |  | BN-P0-011 | Mapped
AI-005 | AI | 005 | Prompt/input gửi provider phải giảm PII và tuân consent/data processing. |  |  | BN-P0-011 | Mapped
AI-006 | AI | 006 | Có timeout, retry giới hạn, circuit breaker, fallback và cost budget. |  |  | BN-P0-011 | Mapped
AI-007 | AI | 007 | AI-generated recipe/community content phải gắn provenance và đi qua validation trước verified status. |  |  | BN-P0-011 | Mapped
AI-008 | AI | 008 | Taste Match/recommendation không được suy luận thuộc tính nhạy cảm ngoài mục đích product. |  |  | BN-P0-011 | Mapped
AI-009 | AI | 009 | Rescue/safety response có rule-based safety layer ưu tiên hơn generative response. |  |  | BN-P0-011 | Mapped
AI-010 | AI | 010 | User có thể hiểu/chỉnh preference đã học và reset personalization. |  |  | BN-P0-011 | Mapped
NFR-PERF-001 | NFR | PERF | API read p95 < 400 ms trong điều kiện bình thường; write p95 < 700 ms, trừ AI/async job. |  |  | Cross-cutting hardening backlog | Mapped
NFR-PERF-002 | NFR | PERF | Recipe detail first meaningful content < 2.5s trên mạng di động phổ biến; cached content nhanh hơn. |  |  | Cross-cutting hardening backlog | Mapped
NFR-PERF-003 | NFR | PERF | Search p95 < 800 ms; autocomplete < 250 ms. |  |  | Cross-cutting hardening backlog | Mapped
NFR-SCALE-001 | NFR | SCALE | Thiết kế hỗ trợ tăng từ 10k → 1M MAU mà không phải rewrite domain model cốt lõi. |  |  | Cross-cutting hardening backlog | Mapped
NFR-AVL-001 | NFR | AVL | Core read/cook flows mục tiêu 99.9% monthly availability; admin/social có thể thấp hơn theo SLO. |  |  | Cross-cutting hardening backlog | Mapped
NFR-REL-001 | NFR | REL | Không mất cook session/feedback/payment event đã acknowledged; dùng idempotency và retry. |  |  | Cross-cutting hardening backlog | Mapped
NFR-OFF-001 | NFR | OFF | Cook Mode cho recipe đã cache hoạt động khi mất mạng; sync eventual khi online. |  |  | Cross-cutting hardening backlog | Mapped
NFR-SEC-001 | NFR | SEC | TLS in transit, encryption at rest, secret manager, MFA bắt buộc cho admin privileged role. |  |  | BN-P0-006 | Mapped
NFR-SEC-002 | NFR | SEC | OWASP ASVS/MASVS-aligned controls; dependency/container scanning trong CI. |  |  | BN-P0-006 | Mapped
NFR-SEC-003 | NFR | SEC | Rate limit, bot/spam protection, abuse detection cho auth/social/public API. |  |  | BN-P0-006 | Mapped
NFR-PRV-001 | NFR | PRV | Data minimization, purpose limitation, consent versioning, export/delete flows. |  |  | Cross-cutting hardening backlog | Mapped
NFR-PRV-002 | NFR | PRV | PII tách khỏi analytics identifiers khi khả thi; log không chứa secret/raw sensitive data. |  |  | Cross-cutting hardening backlog | Mapped
NFR-A11Y-001 | NFR | A11Y | Mục tiêu WCAG 2.2 AA cho web và equivalent accessibility cho mobile. |  |  | Cross-cutting hardening backlog | Mapped
NFR-I18N-001 | NFR | I18N | Toàn bộ UI copy externalized; canonical unit/timezone/locale support. |  |  | Cross-cutting hardening backlog | Mapped
NFR-COMP-001 | NFR | COMP | Web hỗ trợ 2 phiên bản gần nhất Chrome/Edge/Safari/Firefox; mobile hỗ trợ OS policy được công bố. |  |  | Cross-cutting hardening backlog | Mapped
NFR-MNT-001 | NFR | MNT | API versioning, schema migration backward-compatible, feature flag cho rollout rủi ro. |  |  | BN-P0-003, BN-P0-007 | Mapped
NFR-OBS-001 | NFR | OBS | Structured logs, metrics, traces, audit logs và alert theo SLO. |  |  | BN-P0-005 | Mapped
NFR-DR-001 | NFR | DR | RPO mục tiêu <= 15 phút cho transactional DB; RTO <= 4 giờ ở giai đoạn scale, kiểm thử phục hồi định kỳ. |  |  | Cross-cutting hardening backlog | Mapped
NFR-COST-001 | NFR | COST | AI inference có quota/cache/model routing; cost per active user được theo dõi. |  |  | BN-P0-011 | Mapped
NFR-AI-001 | NFR | AI | AI response có timeout/fallback; core recipe/cook không phụ thuộc AI realtime để hoạt động. |  |  | BN-P0-011 | Mapped
NFR-QUAL-001 | NFR | QUAL | Recipe verified phải qua content validation và structured schema validation trước publish. |  |  | Cross-cutting hardening backlog | Mapped
NFR-MOD-001 | NFR | MOD | Report abuse được ghi nhận ngay và moderation queue không mất sự kiện. |  |  | Cross-cutting hardening backlog | Mapped
NFR-DATA-001 | NFR | DATA | Analytics event schema versioned; late/duplicate event xử lý idempotent hoặc dedupe. |  |  | BN-P0-012 | Mapped
NFR-BACKUP-001 | NFR | BACKUP | Backup encrypted, restore test định kỳ và retention nhiều tầng. |  |  | Cross-cutting hardening backlog | Mapped
NFR-UX-001 | NFR | UX | Core flows onboarding → chọn món → cook → feedback không yêu cầu quá nhiều bước; target feedback <=10s. |  |  | Cross-cutting hardening backlog | Mapped
NFR-STORE-001 | NFR | STORE | Mobile đáp ứng yêu cầu App Store/Google Play privacy/billing/permission current policy tại thời điểm release. |  |  | Cross-cutting hardening backlog | Mapped

## Definition of Done
Category | Definition of Done / Gate | Required Evidence
Requirements | Story references requirement ID(s); acceptance criteria agreed before development. | Backlog row + linked test cases
Design | API/data/UX changes reviewed; ADR added for material architectural decisions. | OpenAPI/data migration/ADR/UX review
Code | Implementation follows module boundaries, lint/typecheck passes, no secrets or dead code. | CI logs + code review
Database | Migration forward path tested; destructive changes have safe migration strategy; indexes reviewed. | Migration test + query plan when relevant
Security | Authorization/object ownership validated; inputs/rate limits/uploads reviewed; privileged actions audited. | Security test checklist
Privacy | Purpose/consent/data minimization respected; logs/events scrub sensitive data. | Privacy checklist + event review
AI/Data | Structured output validated; prompt/model/version logged; deterministic guardrail and fallback tested. | Golden tests + fallback test
Testing | Unit + integration + E2E happy/negative cases pass; regression suite updated. | Test report
Performance | No unacceptable regression; critical path p95 target verified where relevant. | Load/perf result
Observability | Relevant logs/metrics/traces/business counters added; alert/runbook updated for critical services. | Dashboard/trace/runbook
Accessibility | UI meets keyboard/screen-reader/text-scale/contrast criteria for impacted surface. | A11y test evidence
Documentation | README/API/data model/runbook/release notes updated. | Docs diff
Release | Feature flag/rollback plan present for risky change; smoke test after deploy. | Release checklist

## Lists
Status | Priority | Phase | Owner
Not Started | Must | P0 Foundation | Unassigned
Ready | Should | P1 Core Cooking | Product
In Progress | Could | P2 Personalization | Frontend
Blocked |  | P3 Household & Planning | Backend
In Review |  | P4 Utility | Data/AI
Done |  | P5 Discovery & Social | QA
Deferred |  | P6 Business & Growth | DevOps
|  | P7 Production & Native | Content
Growth
Security